## RAC Three-Year Work Plan
Task Name | Description | Reliability Risk Priorities | Long-Term Strategy | New | Board Report | Status | Start Date | Target Date | Complete Date | Task Lead | Task Support | Due Y | Comments | Issues & Possible Solutions | Y | Q
Model Development - REPC_C | Develop new plant-controller model is based off of the existing REPC_A model, which interfaces to a single aggregated WTG model. | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | No | No | Complete | 2021-01-01 | 2022-03-31 | 2021-11-29 | MVS | REMWG, ATSMWG | 2022 | Approval Item for the November 30th MVS meeting |  | 2021 | 4
Model Development - WTGWGO_A | Develop a model for auxiliary control to emulate weak grid option (WGO). Some vendors (Siemens-Gamesa in particular) have indicated that in some cases they offer a supplemental control called a WGO. Here we present a simple generic model, as an auxiliary control which can be used to “emulate” this supplemental control | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | No | No | Complete | 2021-01-01 | 2022-03-31 | 2022-01-26 | MVS | REMWG, ATSMWG | 2022 | Approval Item for the November 30th MVS meeting |  | 2022 | 1
Model Development - WTGP_B | Modify the pitch-controller model, which is shown as a proposed new model call WTGP_B | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | No | No | Complete | 2021-01-01 | 2022-12-31 | 2021-11-29 | MVS | REMWG, ATSMWG | 2022 | Approval Item for the November 30th MVS meeting |  | 2021 | 4
Model Development - WTGT_B | Develop a new drive-train “emulation” model where the only input is the electrical power (Pe) of the generator and mechanical power (Pm) is simply taken to be a filtered value of Pe. This should ONLY be used with the type 4A | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | No | No | Complete | 2021-01-01 | 2022-12-31 | 2021-11-29 | MVS | REMWG, ATSMWG | 2022 | Approval Item for the November 30th MVS meeting |  | 2021 | 4
Model Development - WTGIBFFR | Add auxiliary control feature to represent the inertial-based fast-frequency response. | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | No | No | Complete | 2021-01-01 | 2022-12-31 | 2022-01-26 | MVS | REMWG, ATSMWG | 2022 | Approval Item for the November 30th MVS meeting |  | 2022 | 1
Model Development - REGC_C | Develop a proposal for a generator/converter model is an alternative to REGC_B | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | No | No | Complete | 2021-01-01 | 2022-12-31 |  | MVS | REMWG, ATSMWG | 2022 | The model did not meet the criteria for approval. For example, mathematical logic and physical meaning were not clear, and there was no vendor support.
Use of Master Dynamic Model List | Work to ensure approved models are used in the Master Dyanmics file | 6: Committee Specific Priority |  | No | No | Ongoing | 2021-01-01 | 2023-12-31 |  | MVS | REMWG, ATSMWG | 2023
Revise ADS PCM Documentation | Update 2032 ADS PCM Documentation - OneNote -DDVM -Release Notes -Error Checking Protocol -Change Tracker - Process Guide to reflect changes | 6: Committee Specific Priority |  | No | No | Complete | 2021-01-01 | 2022-06-30 |  | PCDS | PCMS | 2022
Collect 2022 LAR resource data | Coordinate with PA on collecting completed LAR resource data targeting the March 2022 data submittal | 6: Committee Specific Priority |  | No | No | Complete | 2021-10-01 | 2022-03-31 | 2022-01-31 | PCDS | WECC PA | 2022 |  |  | 2022 | 1
Pump and Battery Storage Data | Update Pump and Battery Storage Data | 6: Committee Specific Priority |  | No | No | Complete | 2022-01-01 | 2022-03-31 |  | PCDS | PCMS | 2022
Wind, and Solar Hourly Shapes | Work with NREL on developing and Validating Hourly Profiles, starting with historic shapes from year 2018 | 6: Committee Specific Priority |  | Yes | No | Complete | 2021-10-01 | 2022-03-31 | 2022-04-22 | PCDS | PCMS | 2022 |  |  | 2022 | 2
BTM-PV Hourly Profiles | Work with NREL on developing and Validating Hourly profiles, starting with historic shapes from year 2018 | 6: Committee Specific Priority |  | Yes | No | Complete | 2021-10-01 | 2022-05-06 |  | PCDS | PCMS | 2022
Hydro Data | Work with PNNL, BPA and other stakeholders on developing hourly hydro data | 6: Committee Specific Priority |  | Yes | No | Complete | 2021-10-01 | 2022-03-31 | 2022-04-15 | PCDS | PCMS | 2022 |  |  | 2022 | 2
Emission Data | Develop Emission Costs and Emission data for OR-WA | 6: Committee Specific Priority |  | Yes | No | Complete | 2021-10-01 | 2022-03-31 | 2022-04-19 | PCDS | PCMS | 2022 |  |  | 2022 | 2
Utility Tariff and Wheeling rates | Update Utility Tariff and Wheeling rates | 6: Committee Specific Priority |  | No | No | Complete | 2021-10-01 | 2022-03-31 | 2022-01-31 | PCDS | PCMS | 2022 |  |  | 2022 | 1
WECC Path Definitions | Update Path Rating definitions in PCM | 6: Committee Specific Priority |  | No | No | Complete | 2022-01-01 | 2022-03-31 | 2022-04-08 | PCDS | PCMS | 2022 |  |  | 2022 | 2
Fuel and dispatch prices | Update fuel and other dispatch prices | 6: Committee Specific Priority |  | No | No | Complete | 2022-01-01 | 2022-03-31 | 2022-04-15 | PCDS | PCMS | 2022 |  |  | 2022 | 2
Create Load Profiles | Develop the 2032 hourly load forecast | 6: Committee Specific Priority |  | No | No | Complete | 2022-04-01 | 2022-04-30 |  | PCDS | PCMS | 2022
Update Reserves | Update Regulation and Load-Following Reserve shapes (is done after resources and loads have been updated) | 6: Committee Specific Priority |  | No | No | Complete | 2022-05-01 | 2022-05-15 |  | PCDS | PCMS | 2022
Validate 2032 ADS PCM | Initial validation of 2032 ADS PCM | 6: Committee Specific Priority |  | No | No | Complete | 2022-04-01 | 2022-06-30 |  | PCDS | PCMS | 2022
Post 2032 ADS | Post the 2032 ADS (PCM + PF) on June 30, 2022 | 6: Committee Specific Priority |  | No | No | Complete | 2022-06-30 | 2022-06-30 |  | PCDS | PCMS | 2022
Continue Validation of 2032 ADS PCM | Continued validation of 2032 ADS PCM | 6: Committee Specific Priority |  | No | No | Complete | 2022-07-01 | 2022-12-31 |  | PCDS | PCMS | 2022
Revise 2032 ADS PCM Documentation | Update 2032 ADS PCM Documentation - OneNote, DDVM, Release Notes - Process Guide to reflect changes | 6: Committee Specific Priority |  | No | No | Complete | 2021-07-01 | 2022-09-30 |  | PCDS | PCMS | 2022
Request Complete and Timely Resource Data for 2034 ADS | Coordinate with L&R process for collecting resource data for March 2024 submittal | 6: Committee Specific Priority |  | No | No | Proceeding | 2023-07-01 | 2023-09-30 |  | PCDS | LRTF | 2023 | LRTF doesn't exist, need to think about what they were supposed to do.
Develop 2034 ADS | Initiate Development of 2034 Anchor Data Set | 6: Committee Specific Priority |  | No | No | Proceeding | 2023-07-01 | 2024-06-30 |  | PCDS | PCMS, SRS | 2024
2032 ADS Round Trip | Suggestion from the JGC to include something on how the round trip is being incorporated into the WECC data development processes. | 6: Committee Specific Priority | [7 empty] | PCDS |  |  | Need to work with PCDS to verify what this should be and how this should look in the work plan.
Thermal generator data structure enhancement to allow managing generator operation parameters | In-model data management for thermal generator paramters is important for consistency and productivity in PCM development The data management can cover key parameters such as heat rate, minimum up/down time, FOR, ramp rate, derate, etc.. It can help to translate engineers’ experiences to computer processes | 6: Committee Specific Priority |  | No | No | Complete | 2021-04-01 | 2022-02-28 |  | PCMS |  | 2022 | Software implementation has been finished by October 2021. PCMS is working with WECC to conduct validation.
Wheeling and transmission right model enhancement | Wheeling and TR are applied to schedules in actual system, but they impact generator commitment and dispatch; PCM needs to capture the impacts of wheeling and TR on generation dispatch; Two options: one-layer model (current) vs. two-layers model | 6: Committee Specific Priority |  | No | No | Proceeding |  | 2023-12-31 |  | PCMS |  | 2023 | Hitachi Energy and PCMS are exploring options for implementation
Hydro dynamic in simulation | Improve the current hydro data in the ADS PCM to fully utilize the new adaptive K and P calculation function (PCDS) Dynamic hydro schedule and dispatch in cascading system Further enhance the hydro model to accurately reflect the capability of hydro resources to respond renewable integration | 6: Committee Specific Priority |  | No | No | Proceeding |  | 2023-12-31 |  | PCMS | PCDS | 2023 | PCMS and PCDC continue to improve the hydro model in the ADS PCM
PCM automatic data checking and reporting (an enhancement to the current Sanity Check function in GridView) | Create tabulated report for data checing with more instructive description and suggetion for action; Add data checking through data edits | 6: Committee Specific Priority |  | No | No | Proceeding |  | 2023-12-31 |  | PCMS |  | 2023
PCM case merge and split functions | Enables merging different PCM cases, for example, PCM cases from different planning regions Can merge and split based on footprint (e.g. selected area or region) or data type (e.g. selected tables) Can be used in the ADS PCM development, or in planning region’s PCM development and coordination Requires consistent underlying assumptions (such as coincident energy profiles, the same year’s forecast, etc..) Embedded data checking and reporting | 6: Committee Specific Priority |  | No | No | Proceeding |  | 2023-12-31 |  | PCMS |  | 2023 | Not started. PCMS will reevaluate and prioritize this item in 2022
Developing a common system database that include fundamental system data | Include network, load and generator allocation, generator status and type, etc.. ; Can significantly improve consistency and efficiency in both PF and PCM development; Improve long-term consistency in WECC-wide data management; This is also in line with LRTF recommendation to RAC, and requires close coordination among subcommittees, WECC, and software vendors | 6: Committee Specific Priority |  | No | No | Proceeding |  | 2023-12-31 |  | PCMS | PCDS | 2023 | This was originally discussed to facilitate the ADS PCM and PF development and round-trip on a common database. It may have become a part of the WECC-wide effort of the common database development led by WECC. Therefore, PCMS may consider to suspend this item within the PCMS. However, PCMS will continue to evaluate if there will be incremental needs for ADS PCM.
PCM data management and modeling approach enhancments as identified through the ADS PCM development process and planning studies | Every year new enhancements with relatively smaller scope may be identified in order to improve database development and simulation. Therefore the list under this task is dynamically maintained. The items currently identified are: 1. Adding Renewable Inverter Loading Ratio (ILR) 2. Improve hourly profile management with consistent format that is easy to view and revise 3. Allow monitor bus level load based on load ID for the loads on the same bus 4. Dispatchable load, such as DR, EV, etc.. 5. Adding a new feature in GridView to report transmission violation in simulation results | 6: Committee Specific Priority |  | No | No | Proceeding |  | 2023-12-31 |  | PCMS | PCDS | 2023 | The renewable inverter loading ratio function has been implemented in the GV software in 2021, and is expected to be validated by Dec 2021.
Synchrophasor Data | Develop a report that describe the need of synchrophasor data and the challenges with sharing data. | 6: Committee Specific Priority |  | No | No | Proceeding | 2022-01-01 | 2022-09-30 |  | RAC | MVS, SRS, JSIS | 2022 | Report could include potential benefits using synchrophasor data for small signal analysis.
Revise Capitor Cost Calculator | Review and, as necessary, update resource and transmission capital costs | 6: Committee Specific Priority |  | No | No | Proceeding | 2022-03-01 | 2022-09-30 |  | RAC |  | 2022 | Consider moving it to 2023, last updated in 2019
Reliabiltiy Assessments Matrix Review | Review and revise Reliability Assessments Matrix developed by BPSPRTF | 6: Committee Specific Priority |  | No | No | Proceeding | 2022-12-01 | 2023-03-31 |  | RAC |  | 2023 | Do we really see this taking more than a year?
Long-term Planning | The FERC RM21-17 Notice of Proposed Rulemaking calls for long-term scenarios to help the Western Interconnection meet the longterm regional transmission planning requirements. The RAC will be responsible for developing the new scenarios process for this purpose and will ensure the scenarios are incorporated into the committee work. |  |  | Yes | Yes | Proceeding | 2022-10-06 | 2023-06-30 |  | RAC | StS | 2023 | October 6, a workshop was held to give direction to RAC concerning what needs to be done. Some action items were taken from that discussion. Marked as complete since the LPTF has been established.
Steady-state and Dynamics Dashboard (SADD) | Revise Steady-state and Dynamics Dashboard (SADD) to reflect Base case compilation and data check | 6: Committee Specific Priority |  | No | No | Ongoing | 2022-01-01 | 2024-12-31 |  | SRS |  | 2024 | This is tracked and reported at each SRS and RAC meeting.
2023 Base Case Compilation Schedule | Revise Base Case Compilation Schedule and scope of work | 6: Committee Specific Priority |  | No | No | Complete | 2022-07-01 | 2022-09-30 |  | SRS |  | 2022
2023 Data Preparation Manual updates | Revise Data Preparation Manual (Power Flow and Dynamics) - Updated annually with new requirements and information | 6: Committee Specific Priority |  | No | No | Complete | 2022-07-01 | 2022-09-30 |  | SRS |  | 2022
2022 Base Case Compilation and Data Check Report | Develop Annual Base Case Compilation and Data Check Report and review the Annual Base Case Compilation and Data Check Scope of Work | 6: Committee Specific Priority |  | No | No | Complete | 2022-07-01 | 2022-12-31 |  | SRS |  | 2022
2024 Base Case Compilation Schedule | Revise Base Case Compilation Schedule and scope of work | 6: Committee Specific Priority |  | No | No | Complete | 2023-07-01 | 2023-09-30 |  | SRS |  | 2023
2023 Data Preparation Manual updates | Revise Data Preparation Manual (Power Flow and Dynamics) - Updated annually with new requirements and information | 6: Committee Specific Priority |  | No | No | Complete | 2023-07-01 | 2023-09-30 |  | SRS |  | 2023
2024 Base Case Request Survey | Conduct Base Case Request Survey and update Request Form | 6: Committee Specific Priority |  | No | No | Complete | 2023-04-01 | 2023-06-30 |  | SRS |  | 2023
2023 Base Case Compilation and Data Check Report | Develop Annual Base Case Compilation and Data Check Report and review the Annual Base Case Compilation and Data Check Scope of Work | 6: Committee Specific Priority |  | No | No | Proceeding | 2023-07-01 | 2023-12-31 |  | SRS |  | 2023
2025 Base Case Compilation Schedule | Revise Base Case Compilation Schedule and scope of work | 6: Committee Specific Priority |  | No | No | Proceeding | 2024-07-01 | 2024-09-30 |  | SRS |  | 2024
2024 Data Preparation Manual updates | Revise Data Preparation Manual (Power Flow and Dynamics) - Updated annually with new requirements and information | 6: Committee Specific Priority |  | No | No | Proceeding | 2024-07-01 | 2024-09-30 |  | SRS |  | 2024
2025 Base Case Request Survey | Conduct Base Case Request Survey and update Request Form | 6: Committee Specific Priority |  | No | No | Proceeding | 2024-04-01 | 2024-06-30 |  | SRS |  | 2024
2024 Base Case Compilation and Data Check Report | Develop Annual Base Case Compilation and Data Check Report and review the Annual Base Case Compilation and Data Check Scope of Work | 6: Committee Specific Priority |  | No | No | Proceeding | 2024-07-01 | 2024-12-31 |  | SRS |  | 2024
Electromagnetic Transient Modeling | Review if EMT representation is appropriate for RAC data sets. | 6: Committee Specific Priority |  | No | No | Proceeding | 2020-10-07 | 2023-09-30 |  | SRS |  | 2023 | Will need to be updated based on the possible formation of the task force under SRS.
GMD protocol | Make sure GMD protocol is reviewed before each assessment year | 2: Extreme Natural Events |  | No | No | Complete | 2022-01-01 | 2022-12-31 |  | StS |  | 2022
Create 2022-2023 Study Program | Accept study request proposals for 2023 Study Program and decide on appropriate study cases using the 10- and 20-year future scenarios to understand the potential reliability impact to the BES. | 6: Committee Specific Priority |  | No | No | Complete | 2022-07-31 | 2022-09-30 |  | StS |  | 2022
Execute 2022-2023 Study Program | Work with each study team to develop scopes, project plans, studies, metrics for 2023 Study Program for completing each study. Follow up with each group throughout the process. | 6: Committee Specific Priority |  | No | No | Proceeding | 2022-09-01 | 2023-12-31 |  | StS |  | 2023
Report on 2022-2023 Study Program | Determine what reliability concerns each study in the 2023 Study Program has addressed. Assess and approve final reports. | 6: Committee Specific Priority |  | No | No | Proceeding | 2023-10-31 | 2023-12-31 |  | StS |  | 2023 | With the new process perhaps this item should be removed. Is there a way to cancel an item or is it just marked as complete?
GMD Study | Run a GMD study and report back the results | 2: Extreme Natural Events |  | No | No | Complete | 2022-01-01 | 2022-12-31 |  | StS |  | 2022 | This is done every 2nd and 5th year. 2022, 2024, 2027, 2030
GMD protocol | Make sure GMD protocol is reviewed before each assessment year | 2: Extreme Natural Events |  | No | No | Proceeding | 2024-01-01 | 2024-12-31 |  | StS |  | 2024 | This is done every 2nd and 5th year. 2022, 2024, 2027, 2030
GMD Study | Run a GMD study and report back the results | 2: Extreme Natural Events |  | No | No | Proceeding | 2024-01-01 | 2024-12-31 |  | StS |  | 2024 | This is done every 2nd and 5th year. 2022, 2024, 2027, 2030
Create 2043 WECC Scenarios | Revisit Scenarios and see if they need to be updated | 6: Committee Specific Priority |  | No | No | Complete | 2022-01-01 | 2022-12-31 |  | SWG | StS | 2022
UFLSWG Report | UFLSWG Studies and Report | 6: Committee Specific Priority |  | No | No | Complete | 2021-01-01 | 2022-12-31 |  | UFLSWG | StS | 2022
2022 UFLS Assessment Mitigation | UFSLWG to identify and execute mitigation of the issues identified in the 2022 UFLS assessment. | 5: Other Risk(s) |  | Yes | No | Proceeding | 2022-11-01 | 2023-12-31 |  | UFLSWG | StS | 2023
Perform Assessments | Studies Subcommittee performs assessments as needed. As new assessments are identified they will be added to the workplan. | 6: Committee Specific Priority |  | Yes | Yes | Ongoing | 2024-01-01 | 2026-12-31 |  | StS |  | 2026
Grid Forming Inverter Model | Generic vendor agnostic grid forming inverter models for positive sequence studies | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | Yes | No | Proceeding | 2023-01-01 | 2023-10-31 |  | MVS |  | 2023
REEC_E | Electrical controller model for use with wind, PV and BESS. | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | Yes | No | Proceeding | 2024-01-01 | 2024-12-31 |  | MVS |  | 2024
REPC_D | Plant controller model interfaced with multiple aggregated renewable system models downstream | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | Yes | No | Proceeding | 2024-01-01 | 2024-12-31 |  | MVS |  | 2024
VHVDC2 | Generic simple point-to-point VSC-HVDC model updated with feedback from Transbay Cable. | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | Yes | No | Proceeding | 2024-01-01 | 2024-12-31 |  | MVS |  | 2024
SVSMO4 | Hybrid-STATCOM model | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | Yes | No | Proceeding | 2024-01-01 | 2024-12-31 |  | MVS |  | 2024
VHVDC3 | Off-shore winds DC | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | Yes | No | Proceeding | 2024-01-01 | 2024-12-31 |  | MVS |  | 2024
SCMOV | Series capacitor MOV model | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | Yes | No | Proceeding | 2024-01-01 | 2024-12-31 |  | MVS |  | 2024
Multi-Terminal HVDC VSC model | Multi-Terminal Voltage Source Converter High Voltage Direct Current | 4: Impacts of Changing Resources and Customer Loads on the BPS |  | Yes | No | Proceeding | 2024-01-01 | 2024-12-31 |  | MVS |  | 2024
2024 Base Case Compilation and Data Check Report | Develop Annual Base Case Compilation and Data Check Report and review the Annual Base Case Compilation and Data Check Scope of Work | 6: Committee Specific Priority |  | No | No | Proceeding | 2024-07-01 | 2024-12-31 |  | SRS |  | 2024
2026 Base Case Compilation Schedule | Revise Base Case Compilation Schedule and scope of work | 6: Committee Specific Priority |  | No | No | Proceeding | 2025-07-01 | 2025-09-30 |  | SRS |  | 2025
2025 Data Preparation Manual updates | Revise Data Preparation Manual (Power Flow and Dynamics) - Updated annually with new requirements and information | 6: Committee Specific Priority |  | No | No | Proceeding | 2025-07-01 | 2025-09-30 |  | SRS |  | 2025
2026 Base Case Request Survey | Conduct Base Case Request Survey and update Request Form | 6: Committee Specific Priority |  | No | No | Proceeding | 2025-04-01 | 2025-06-30 |  | SRS |  | 2025
2025 Base Case Compilation and Data Check Report | Develop Annual Base Case Compilation and Data Check Report and review the Annual Base Case Compilation and Data Check Scope of Work | 6: Committee Specific Priority |  | No | No | Proceeding | 2025-07-01 | 2025-12-31 |  | SRS |  | 2025
Request Complete and Timely Resource Data for 2036 ADS | Coordinate with L&R process for collecting resource data for March 2026 submittal | 6: Committee Specific Priority |  | No | No | Proceeding | 2025-07-01 | 2025-09-30 |  | PCDS |  | 2025
Develop 2036 ADS | Initiate Development of 2036 Anchor Data Set | 6: Committee Specific Priority |  | No | No | Proceeding | 2025-07-01 | 2026-06-30 |  | PCDS |  | 2026