## Post-Release Issues
Issue/Observation | Recommendations | Lead Responsibility | Expected completion date | Status/Comments
Reserve requirements have not been revised from 2030 ADS | Create reserve requirements | PNNL |  | To be updated by PNNL
Explain or resolve capacity differences between the PCM, L&R and PF | Used VAR Margin Ration to Lower PCM to match PF |  |  | Complete
There are discrepancies between PV and L&R for Columbia River Gorge units including Grand Coulee | Resolve discrepancies between PF and L&R capacities |  |  | Bring to PCDS
Round trip export capability out of GV doesn't read into PSLF | Correct GridView to enable ability to read exported hour into PSLF | Hitachi
Update Demand Response Shapes to integrate into case |  | LBNL, staff |  | Complete
Batteries are modeled as pump storage in GridView | Consider using the new battery model in GridView
Capacities - If we reference a Heavy Summer PF case for the PCM, the ratings will be derated for summer vs referencing a Winter PF case
The high CO2 cost provided by AESO results in Alberta importing heavy from the US market. Given the uncertainty in this developing CO2 market PCDS | Change to BC CO2 price |  |  | Complete
There exist uncertainty as to the future of Colstrip 3 and 4. Some of the current owners have reported terminating/retiring their share of Colstrip facility. Currently x MW are reported in the L&R there the PCDS recommended that only one unit be operational in the base case (Unit 4). WECC has provided a two scenario, one to turn on Colstrip 3 and the second to turn off Colstrip 4 | Adopt consistent assumptions regarding Colstrip retirements | PCDS
Non dispatchable supply. The PCDS has not approved assumptions regarding the modeling of geothermal supply. Currently it is modeled as dispatchable with a zero cost dispatch cost. A scenario is provided to convert geothermal supply to fix energy supply where monthly generation is based on historic five year average generation by month. | Approve assumptions on modeling geothermal supply | PCDS
Possible Path 42 rating increase | Create change file with rating of 1,400 MW
DCI - Virgina - Smith (0MW into WECC every hour). Should this be modified?
PF, PCM, and L&R differ. Need to know what to do when PCM capacity is lower than L&R.
Facilities with multiple owners have different assumptions about retirement dates | Resolve discrepancies regarding retirement dates between owners
OR and WA have raised concerns about the case using a CO2 price of $0 | Clarify that the current price is $0 but can be changed via change cases
LADWP DMS disagreement | LADWP said to leave as is |  |  | Complete
Pumped Storage Generic in CISO. How much pondage, etc. What should parameters be?
NEVP Basecase Modification | Integrated into case |  |  | Complete
Derate2 and Derate3 have whole numbers instead of percentage | Correct the derate to a percentage |  |  | Complete
There is uncertainty about whether the Craig unit, currently not in the case, should be retired. | Determine whether Craig should be retired. |  |  | In email from WACM, they suggested to not include since it will most likely be retired
Tracy pump modeled as load in PF an generators in PCM | Resolve between Hitachi and PCDS |  |  | Change case created to turn off loads in PCM
Changes to bus and or Gen ID for some units to algin with PF |  |  |  | Change case created
DCI Stegall, Artesia, and Miles City are modeled as load in PF and generators in the PCM | Post processing?
PSCO Generator Updates
CFE generator Updates