## Pre-Release Issues
Issue/Observation | Resolution for Approved ADS Case | Timeline | Assignment | Recommendations | Persons Responsible | Expected completions date | Status
Some resources show different capacities in the PF and L&R data | To be decided by PCDS. To be discussed at 8-3-2022 PCDS meeting | 08-03: Decision at PCDS If changes needed, staff to implement by 08-12 |  | If close - no action, If grossly different - VAR Margin Ratio to reduce Pmax. If CC gen has duct burner, use PF Pmax or Nameplate | Jon, Tyler, BK, Bhavana, Stan | 2022-08-10 | Complete. WECC staff has updated capacities according to the rule approved by the PCDS on 08-03-2022. New capacity values are included in the case posted 08-12-2022.
The current case includes unserved energy (USE) for WACM, PSCO, CFE. The amount is very small (maximum hourly unserved load less than 6%, annual unserved load less than 0.01%) | Eliminate all unserved load |  |  | Validate that min up/down times, available generation, unit commitment are correct for each BA ) Transmission constraints. Look into ESL… CFE combined cylce plant 2 CTs and ST unit, only one CT in PCM case. Check CFE Thermal fuels | BK, Jon, Tyler | 2022-08-10 | Complete. The case that was run between August 12 and August 15 showed no unserved energy.
The case includes significant congestion on Transmission Path 83, Path 1, and Path 42 (over 7,000 hours) | Explaination for high unserved load hours |  |  | WECC can create a change case if needed for a different CO2 price for Alberta | Jon, Tyler, BK, Bhavana, Stan | 2022-08-10 | Complete. In the most recent case that was run, Path 42 showed over 7,000 hours of congestion due to a dispute about the Path's rating. Other congestion data is within reasonable values.
Address the modeling of MATLB Phase Shifter (Path 83) (May need to be modeled to help flow to Alberta) | What is the desired resolution--explanation? |  |  | Not currently modeled in PF or PCM, model as phase shifter, Check with Nick. Update type -4 PS to type 4 in PCM. Tell Jin | Jon, Tyler | 2022-08-10 | Complete.
Alberta CO2 price is twice the value of other areas | Confirm with Alberta that the value is correct or change it to the value for other parts of the Western Interconnection | 08-03: Decision at PCDS If changes needed, staff to implement by 08-05 | Contact Alberta to validate CO2 price (who?) | Do we change it to California, BC, or other lower value? Account for Alberta Offsets, canadian dollars/exchange rate | Stan | 2022-08-05 | Complete. PCDS decided at 08-03-2022 PCDS meeting to keep the current Alberta CO2 values in the case, as they have been verified by AESO. WECC will also publish change cases with other values for stakeholders who want to use them.
LADWP non-firm DSM is much higher than other DSM in the SCE area | Either confirm with LADWP that values are correct or adjust to SCE-area values |  | Follow up with LADWP to validate DSM values (who?) | Reach out to LADWP, they say keep as is | Tyler | 2022-08-05 | Complete: LADWP has verified that this is correct--no changes.
Some 230 kv and above lines and transformers are not monitored | Monitor the lines and transformers in the case |  | Update the case to monitor all 230 kv and above lines and transformers |  | Jon | 2022-08-05 | Complete. WECC has verified that running a case with all 230 kv and above facilities monitored increases the run time to an unacceptable level. The approved case will include monitoring for the approved list of facilities. WECC will also post a case with all 230 kv and above faciliites monitored for stakeholders who would like to use it.
The daily operating range for BPA hydro units is three times that of the weekly operating ranges. (What is the effect on the dispatch?) | No additional changes needed |  |  | Already updated in case. Check inputs. It is what it is | BK, Bhavana | 2022-08-05 | Complete. BPA operating ranges have been verified in the case.
Clean out unreferenced DAT files, bus connection problems and unit IDs. | Unneeded files removed from the case |  | Remove unneeded files (who?) | Previous efforts to do this created issues with the case not solving. It may be acceptable to leave the files in the case. Unique bus number and IDs. Check to make sure they are in the Distrubution Table | Jon, BK | 2022-08-10 | In Progress. Files will be removed by 08-17-2022.
Many LMPs appear to be very high | Explain high LMPs |  |  | Look into transmission congestion and unserved load | BK, Stan | 2022-08-10 | Complete. Average systemwide LMP is $150/mwh and congestion is reasonable.
Investigate the Operation of Phase Shifters, Pump Storage, Batteries, etc. | Correct Path 83 phase shifter to MATLB |  | Clarify this issue in relation to the Alberta issue |  | BK, Jon, Tyler | 2022-08-10 | Complete. Phase shifer operations, pump storage performance and battery performance are the result of the case based on inputs.
Exports from BC to Alberta are very high | Explain why BC-to-Alberta exports are high |  | Validate the load/resource balance for Alberta (who) |  | Stan, Jon, BK, Bhavana | 2022-08-10 | Complete. Concern is the result of Alberta CO2 price. PCDS decided at 08-03-2022 PCDS meeting to keep the current Alberta CO2 values in the case, as they have been verified by AESO. WECC will also publish change cases with other values for stakeholders who want to use them.
Northwest to BC, Path 3, flows into BC |  |  |  | Investigate | Stan, Tyler, Jon, BK, Bhavana | 2022-08-05 | Complete. Concern is the result of the hydro energies in the monthly variable schedule in BC. The data is the best we have. There is a slight impact from the AESO CO2 prices.
PF export from GV is not in a correct format for PSLF and won't read into PSLF | [6 empty] | In progress. WECC staff is working with Hitachi to resolve this issue.