## Other Data Schedule
Version | Version Other Data Items | Other Data Items | Original Index | Current Data Used | Data Availability - Date | Last Updated | Decision/Date (when we made the decision) | Action/Notes | Contacts | Incremental Updates | Implementation Schedule ADS-Begin | Implementation Schedule ADS-End | Days from start | 2023-01-01 | Implementatin Number of Days | 2024-01-31 | 45322
V1 | V1_BC Hydro Data | BC Hydro Data | 9 |  |  | Older vintage | Update if available, ask BC Hydro for update | Recalculation - Taylor dispatch to support new load data for 2023 and 2024. Ask Nathalie Voisin and PNNL. If we can define a process, we can ask hitachi to make GV enhancement |  | Ask BC for updates, PNNL, Nathalie Voisin | 2023-05-24 | 2023-06-07 | 143 | 2023-05-24 | 14
V1 | V1_Load Shapes | Load Shapes | 10 | 2018 shape and 2022 L&R monthly peak and energy | March-April | 2022-04-01 | Update load forecast | Still using 2018 base year, but updated based on latest L&R, peak and energy |  |  | 2023-06-07 | 2023-07-12 | 157 | 2023-06-07 | 35
V1 | V1_ Demand Response Shapes | Demand Response Shapes | 11 | LBNL based off available DR from L&R and LMPs form 2032 ADS run |  | 2022-08-01 | Update at end of build | May need to have GV to dispatch |  |  | 2023-07-12 | 2023-07-19 | 192 | 2023-07-12 | 7
V1 | V1_ Energy Efficiency | Energy Efficiency | 12 | Not used in 2032 |  | None | Update as needed, if available | Built into the load forecast, AAEE for CA, need CEC data |  |  | 2023-07-12 | 2023-07-19 | 192 | 2023-07-12 | 7
V1 | V1_ Electric Vehicle loads | Electric Vehicle loads | 14 | N/A |  | None | Updated if available | For CA layer in unique load shape as needed. Ask CA what they want to do for 2023. V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2023-07-12 | 2023-07-19 | 192 | 2023-07-12 | 7
V1 | V1_ Electrification Loads | Electrification Loads | 15 | N/A |  | None | Updated if available | For CA layer in unique load shape as needed. V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2023-07-12 | 2023-07-19 | 192 | 2023-07-12 | 7
V1 | V1_Transmission Contingencies | Transmission Contingencies | 4 | N/A |  | None | Discuss Further | TBD |  |  | 2023-07-19 | 2023-08-02 | 199 | 2023-07-19 | 14
V1 | V1_Phase Shifter Transformers - How to treat, and review | Phase Shifter Transformers - How to treat, and review | 40 |  |  |  | Discuss Further |  |  |  | 2023-07-19 | 2023-08-02 | 199 | 2023-07-19 | 14
V1 | V1_ BTM PV | BTM PV | 16 |  |  |  | Updated if available | V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2023-08-02 | 2023-08-16 | 213 | 2023-08-02 | 14
V1 | V1_ BTM Storage | BTM Storage | 17 |  |  |  | Updated if available | V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2023-08-02 | 2023-08-16 | 213 | 2023-08-02 | 14
V1 | V1_Hourly Wind Shapes | Hourly Wind Shapes | 18 | NREL |  | 2022-05-01 | Update if needed, planned resources | review data quality with NREL to see if there is updated data. This is for new or units with missing data. V2 incremental changes | Anthony Lopez, Greg Brinkeman | Update with Wind Toolkit Data, test with units we have had issues with | 2023-08-16 | 2023-09-13 | 227 | 2023-08-16 | 28
V1 | V1_Hourly Utility Scale Solar shapes | Hourly Utility Scale Solar shapes | 19 | NREL |  | 2022-05-01 | Add shapes for new planned resources | Incemental updates for V1 and V2 |  |  | 2023-08-16 | 2023-09-13 | 227 | 2023-08-16 | 28
V1 | V1_Thermal Plant Data | Thermal Plant Data | 21 | [7 empty] | 2023-09-13 | 2023-09-27 | 255 | 2023-09-13 | 14
V1 | V1_ Cycling Data (Start costs, other) | Cycling Data (Start costs, other) | 22 | 2020 Intertek Report |  | 2020-05-01 | Check with Intertek on frequency of updates | Check with Intertek, only do once, either V1 or V2 |  |  | 2023-09-13 | 2023-09-27 | 255 | 2023-09-13 | 14
V1 | V1_ Min up/down time | Min up/down time | 23 |  |  | 2020-05-01 | Check with Intertek on frequency of updates |  |  |  | 2023-09-13 | 2023-09-27 | 255 | 2023-09-13 | 14
V1 | V1_ Ramp Rates | Ramp Rates | 24 | 2020 Intertek Report |  | 2020-05-01 | Check with Intertek on frequency of updates |  |  |  | 2023-09-13 | 2023-09-27 | 255 | 2023-09-13 | 14
V1 | V1_ Heat rates | Heat rates | 25 | CEC and Kevin Harris analysis of CEMS data |  | 2020-06-01 | Check with Intertek on frequency of updates |  |  |  | 2023-09-27 | 2023-10-11 | 269 | 2023-09-27 | 14
V1 | V1_BTM PV Shapes and modeling methodology | BTM PV Shapes and modeling methodology | 20 | NREL |  | 2022-05-01 | Needs to be evaluated. Update magitude, not the shapes | County by utility bus vs Area granularity |  |  | 2023-10-11 | 2023-10-25 | 283 | 2023-10-11 | 14
V1 | V1_FOR | FOR | 27 | GADS pc-GAR |  | 2022-01-01 | Update, GADS PCgar | GADS pcgar |  |  | 2023-10-11 | 2023-10-25 | 283 | 2023-10-11 | 14
V1 | V1_Path definitions/ratings - WECC Paths | Path definitions/ratings - WECC Paths | 1 | 2022 Path Rating Catalog | April | 2022-04-01 | Update with Path Rating Catalog | Include any Phase 3, maybe 2B transmision project |  | Minor-incremental updates from 2023 PRC | 2023-10-25 | 2023-11-08 | 297 | 2023-10-25 | 14
V1 | V1_Review all interfaces - Non WECC Paths | Review all interfaces - Non WECC Paths | 2 |  |  |  | Review definitions - working session PCDS | Review definitions |  |  | 2023-10-25 | 2023-11-08 | 297 | 2023-10-25 | 14
V1 | V1_Transmission Nomograms | Transmission Nomograms | 3 | BPA provided Path 8 nomogram |  |  | Discuss Further- ask for updates | ask TEPC and EPE for updates |  | Minor - updates to nomogram | 2023-11-08 | 2023-11-22 | 311 | 2023-11-08 | 14
V1 | V1_EPE and TEPC load and generation balance nomograms | EPE and TEPC load and generation balance nomograms | 5 | Generation from L&R and confirmation from WestConnect |  |  | Update - 3/15/2023 | Verify proper modeling, send to EPE and TEPC, review list of supply for feedback |  | Minor - updates to nomogram | 2023-11-08 | 2023-11-22 | 311 | 2023-11-08 | 14
V1 | V1_Wheeling Rates (from utility tariffs) | Wheeling Rates (from utility tariffs) | 6 | Utility OASIS data |  | 2021-12-01 | Check and Update as necessary |  |  |  | 2023-11-22 | 2023-12-20 | 325 | 2023-11-22 | 28
V2 | V2_ Natural Gas Prices | Natural Gas Prices | 28 | CEC 2021 IEPR | December | 2022-02-01 | Update | Make change case available if data is available for V1 |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V2 | V2_ Coal Prices | Coal Prices | 29 | Inflated 2030 ADS prices |  | 2022-02-01 | Update |  |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V2 | V2_ Uranium Prices | Uranium Prices | 30 | 2022 Price |  | 2022-02-01 | Update |  |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V2 | V2_ Other fuels Prices | Other fuels Prices | 31 | Inflated 2030 ADS prices |  | 2022-02-01 | Update |  |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V2 | V2_Deflator/Inflator rates | Deflator/Inflator rates | 37 | Moody's inflator |  | 2022-02-01 | Update | Ask CEC if deflator series changes every year, otherwise just do once |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V1 | V1_Deflator/Inflator rates | Deflator/Inflator rates | 77 | Moody's inflator |  | 44593 | Update | Ask CEC if deflator series changes every year, otherwise just do once |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V2 | V2_Path definitions/ratings - WECC Paths | Path definitions/ratings - WECC Paths | 41 | 2022 Path Rating Catalog | April | 44652 | Update with Path Rating Catalog | Include any Phase 3, maybe 2B transmision project |  | Minor-incremental updates from 2023 PRC | 2024-01-03 | 2024-02-14 | 367 | 2024-01-03 | 42
V2 | V2_CO2 prices California | CO2 prices California | 32 | CEC 2021 IEPR | December | 2022-04-01 | Update |  |  |  | 2024-01-17 | 2024-01-31 | 381 | 2024-01-17 | 14
V2 | V2_CO2 prices Washington Oregon | CO2 prices Washington Oregon | 33 |  |  | NA | Update, reach out to BPA |  |  |  | 2024-01-17 | 2024-01-31 | 381 | 2024-01-17 | 14
V2 | V2_CO2 prices BC and Alberta | CO2 prices BC and Alberta | 34 |  |  |  | Update |  |  |  | 2024-01-17 | 2024-01-31 | 381 | 2024-01-17 | 14
V2 | V2_BC Hydro Data | BC Hydro Data | 49 |  |  | Older vintage | Update if available, ask BC Hydro for update | Recalculation - Taylor dispatch to support new load data for 2023 and 2024. Ask Nathalie Voisin and PNNL. If we can define a process, we can ask hitachi to make GV enhancement |  | Ask BC for updates, PNNL, Nathalie Voisin | 2024-01-31 | 2024-02-14 | 395 | 2024-01-31 | 14
V1 | V1_Variable O&M for all thermal generator types | Variable O&M for all thermal generator types | 66 |  |  |  | Check with Intertek |  |  |  | 2024-01-31 | 2024-02-14 | 395 | 2024-01-31 | 14
V1 | V1_Variable O&M for all Non-thermal generator types | Variable O&M for all Non-thermal generator types | 75 | INTERTEK Cycleing Cost Report |  | 44440 | Update |  |  |  | 2024-01-31 | 2024-02-14 | 395 | 2024-01-31 | 14
V2 | V2_Load Shapes | Load Shapes | 50 | 2018 shape and 2022 L&R monthly peak and energy | March-April | 44652 | Update load forecast | Still using 2018 base year, but updated based on latest L&R, peak and energy |  |  | 2024-02-14 | 2024-03-13 | 409 | 2024-02-14 | 28
V1 | V1_Dispatch price for wind, solar, and hydro (Also called oportunity cost) | Dispatch price for wind, solar, and hydro (Also called oportunity cost) | 76 | INTERTEK Cycleing Cost Report |  | 44440 | Update |  |  |  | 2024-02-14 | 2024-02-28 | 409 | 2024-02-14 | 14
V2 | V2_Load-Following and Regulation reserve calculations | Load-Following and Regulation reserve calculations | 38 | PNNL |  | 2023-03-01 |  | PNNL |  |  | 2024-03-13 | 2024-04-24 | 437 | 2024-03-13 | 42
V2 | V2_ Demand Response Shapes | Demand Response Shapes | 51 | LBNL based off available DR from L&R and LMPs form 2032 ADS run |  | 44774 | Update at end of build | May need to have GV to dispatch |  |  | 2024-03-13 | 2024-03-27 | 437 | 2024-03-13 | 14
V2 | V2_ Energy Efficiency | Energy Efficiency | 52 | Not used in 2032 |  | None | Update as needed, if available | Built into the load forecast, AAEE for CA, need CEC data |  |  | 2024-03-13 | 2024-03-27 | 437 | 2024-03-13 | 14
V2 | V2_Maintenance Schedule | Maintenance Schedule | 39 | WECC |  | 2022-07-01 | Update |  |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V2 | V2_ Electric Vehicle loads | Electric Vehicle loads | 54 | N/A |  | None | Updated if available | For CA layer in unique load shape as needed. Ask CA what they want to do for 2023. V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V2 | V2_ Electrification Loads | Electrification Loads | 55 | N/A |  | None | Updated if available | For CA layer in unique load shape as needed. V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V2 | V2_ BTM PV | BTM PV | 56 |  |  |  | Updated if available | V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V2 | V2_ BTM Storage | BTM Storage | 57 |  |  |  | Updated if available | V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V1 | V1_Maintenance Schedule | Maintenance Schedule | 79 | WECC |  | 44743 | Update |  |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V2 | V2_Hourly Wind Shapes | Hourly Wind Shapes | 58 | NREL |  | 44682 | Update if needed, planned resources | review data quality with NREL to see if there is updated data. This is for new or units with missing data. V2 incremental changes | Anthony Lopez, Greg Brinkeman | Update with Wind Toolkit Data, test with units we have had issues with | 2024-04-10 | 2024-04-24 | 465 | 2024-04-10 | 14
V2 | V2_Hourly Utility Scale Solar shapes | Hourly Utility Scale Solar shapes | 59 | NREL |  | 44682 | Add shapes for new planned resources | Incemental updates for V1 and V2 |  |  | 2024-04-10 | 2024-04-24 | 465 | 2024-04-10 | 14
V2 | V2_BTM PV Shapes and modeling methodology | BTM PV Shapes and modeling methodology | 60 | NREL |  | 44682 | Needs to be evaluated. Update magitude, not the shapes | County by utility bus vs Area granularity |  |  | 2024-04-10 | 2024-04-24 | 465 | 2024-04-10 | 14
V2 | V2_Coincident Energy Year Shapes | Coincident Energy Year Shapes | 7 | Year 2018 |  | 2021-07-01 | No change for this cycle | No change for this cycle. Keep 2018 as the year |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_Hydro Data (Weekly energy, min, max, etc.) | Hydro Data (Weekly energy, min, max, etc.) | 8 | Actual 2018 data and BPA models using 2018 as base |  | 2022-04-01 | No change for this cycle | No change for this cycle |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_ Pump loads | Pump loads | 13 | 2018 actuals obtained from CISO |  | 2022-02-01 | No change for this cycle | No change for this cycle |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_Variable O&M for all thermal generator types | Variable O&M for all thermal generator types | 26 |  |  |  | No change for V2 | No change for V2 |  |  | None |  | 0 | 2023-01-01 | 0
V2 | V2_Variable O&M for all Non-thermal generator types | Variable O&M for all Non-thermal generator types | 35 | INTERTEK Cycleing Cost Report |  | 2021-09-01 | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_Dispatch price for wind, solar, and hydro (Also called oportunity cost) | Dispatch price for wind, solar, and hydro (Also called oportunity cost) | 36 | INTERTEK Cycleing Cost Report |  | 2021-09-01 | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_Review all interfaces - Non WECC Paths | Review all interfaces - Non WECC Paths | 42 |  |  |  | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_Transmission Nomograms | Transmission Nomograms | 43 | BPA provided Path 8 nomogram |  |  | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_Transmission Contingencies | Transmission Contingencies | 44 | N/A |  | None | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_EPE and TEPC load and generation balance nomograms | EPE and TEPC load and generation balance nomograms | 45 | Generation from L&R and confirmation from WestConnect |  |  | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_Wheeling Rates (from utility tariffs) | Wheeling Rates (from utility tariffs) | 46 | Utility OASIS data |  | 44531 | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V1 | V1_Coincident Energy Year Shapes | Coincident Energy Year Shapes | 47 | Year 2018 |  | 44378 | No change for this cycle | No change for this cycle. Keep 2018 as the year |  |  | None | None | 0 | 2023-01-01 | 0
V1 | V1_Hydro Data (Weekly energy, min, max, etc.) | Hydro Data (Weekly energy, min, max, etc.) | 48 | Actual 2018 data and BPA models using 2018 as base |  | 44652 | No change for this cycle | No change for this cycle |  |  | None | None | 0 | 2023-01-01 | 0
V1 | V1_ Pump loads | Pump loads | 53 | 2018 actuals obtained from CISO |  | 44593 | No change for this cycle | No change for this cycle |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_Thermal Plant Data | Thermal Plant Data | 61 | [7 empty] | None | None | 0 | 2023-01-01 | 0
V2 | V2_ Cycling Data (Start costs, other) | Cycling Data (Start costs, other) | 62 | 2020 Intertek Report |  | 43952 | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_ Min up/down time | Min up/down time | 63 |  |  | 43952 | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_ Ramp Rates | Ramp Rates | 64 | 2020 Intertek Report |  | 43952 | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_ Heat rates | Heat rates | 65 | CEC and Kevin Harris analysis of CEMS data |  | 43983 | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_FOR | FOR | 67 | GADS pc-GAR |  | 44562 | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
V1 | V1_ Natural Gas Prices | Natural Gas Prices | 68 | CEC 2021 IEPR | December | 44593 | No change for V1 | No change for V1 |  |  | None | None | 0 | 2023-01-01 | 0
V1 | V1_ Coal Prices | Coal Prices | 69 | Inflated 2030 ADS prices |  | 44593 | No change for V1 | No change for V1 |  |  | None | None | 0 | 2023-01-01 | 0
V1 | V1_ Uranium Prices | Uranium Prices | 70 | 2022 Price |  | 44593 | No change for V1 | No change for V1 |  |  | None | None | 0 | 2023-01-01 | 0
V1 | V1_ Other fuels Prices | Other fuels Prices | 71 | Inflated 2030 ADS prices |  | 44593 | No change for V1 | No change for V1 |  |  | None | None | 0 | 2023-01-01 | 0
V1 | V1_CO2 prices California | CO2 prices California | 72 | CEC 2021 IEPR | December | 44652 | No change for V1 | No change for V1 |  |  | None | None | 0 | 2023-01-01 | 0
V1 | V1_CO2 prices Washington Oregon | CO2 prices Washington Oregon | 73 |  |  | NA | No change for V1 | No change for V1 |  |  | None | None | 0 | 2023-01-01 | 0
V1 | V1_CO2 prices BC and Alberta | CO2 prices BC and Alberta | 74 |  |  |  | No change for V1 | No change for V1 |  |  | None | None | 0 | 2023-01-01 | 0
V1 | V1_Load-Following and Regulation reserve calculations | Load-Following and Regulation reserve calculations | 78 | PNNL |  | 44986 | No change for V1 | No change for V1 |  |  | None | None | 0 | 2023-01-01 | 0
V2 | V2_Phase Shifter Transformers - How to treat, and review | Phase Shifter Transformers - How to treat, and review | 80 |  |  |  | No change for V2 | No change for V2 |  |  | None | None | 0 | 2023-01-01 | 0
Formulas:
Implementation Schedule ADS-Begin = XLOOKUP([Version Other Data Items],'PCDS Schedule'!B:B,'PCDS Schedule'!E:E)
Implementation Schedule ADS-End = XLOOKUP([Version Other Data Items],'PCDS Schedule'!B:B,'PCDS Schedule'!K:K)
Days from start = IFERROR(DAYS([Implementation Schedule ADS-Begin],P1),)
Implementatin Number of Days = IFERROR(DAYS([Implementation Schedule ADS-End],[Implementation Schedule ADS-Begin]),0)

## PCDS Meeting Schedule
PCDS Meeting | Discussion | Approval of Methodology | Notes | Discussion1 | Discussion2 | Discussion3 | Discussion4 | Discussion5 | Discussion6 | Discussion7 | 4 Weeks1 | 4 Weeks2 | 4 Weeks3 | 4 Weeks4 | 6 Weeks1 | 6 Weeks2 | 6 Weeks3 | 6 Weeks4 | Approvals1 | Approvals2 | Approvals3 | Approvals4 | Approvals5 | Approvals6 | Approvals7
2023-04-26
2023-05-10
2023-05-24 | V1_BC Hydro Data |  |  | V1_BC Hydro Data
2023-06-07 | V1_Load Shapes | V1_BC Hydro Data |  | V1_Load Shapes | [14 empty] | V1_BC Hydro Data
2023-06-21 | V1_Load Shapes | [9 empty] | 4 Weeks1: V1_Load Shapes
2023-07-12 | V1_ Demand Response Shapes V1_ Energy Efficiency V1_ Electric Vehicle loads V1_ Electrification Loads | V1_Load Shapes |  | V1_ Demand Response Shapes | V1_ Energy Efficiency | V1_ Electric Vehicle loads | V1_ Electrification Loads | [11 empty] | V1_Load Shapes
2023-07-19 | V1_Transmission Contingencies V1_Phase Shifter Transformers - How to treat, and review | V1_ Demand Response Shapes V1_ Energy Efficiency V1_ Electric Vehicle loads V1_ Electrification Loads |  | V1_Transmission Contingencies | V1_Phase Shifter Transformers - How to treat, and review | [13 empty] | V1_ Demand Response Shapes | V1_ Energy Efficiency | V1_ Electric Vehicle loads | V1_ Electrification Loads
2023-08-02 | V1_ BTM PV V1_ BTM Storage | V1_Transmission Contingencies V1_Phase Shifter Transformers - How to treat, and review |  | V1_ BTM PV | V1_ BTM Storage | [13 empty] | V1_Transmission Contingencies | V1_Phase Shifter Transformers - How to treat, and review
2023-08-16 | V1_Hourly Utility Scale Solar shapes V1_Hourly Wind Shapes | V1_ BTM PV V1_ BTM Storage |  | V1_Hourly Utility Scale Solar shapes | V1_Hourly Wind Shapes | [13 empty] | V1_ BTM PV | V1_ BTM Storage
2023-08-30 | V1_Hourly Utility Scale Solar shapes V1_Hourly Wind Shapes | [9 empty] | 4 Weeks1: V1_Hourly Utility Scale Solar shapes; 4 Weeks2: V1_Hourly Wind Shapes
2023-09-13 | V1_Thermal Plant Data V1_ Cycling Data (Start costs, other) V1_ Min up/down time V1_ Ramp Rates | V1_Hourly Utility Scale Solar shapes V1_Hourly Wind Shapes |  | V1_Thermal Plant Data | V1_ Cycling Data (Start costs, other) | V1_ Min up/down time | V1_ Ramp Rates | [11 empty] | V1_Hourly Utility Scale Solar shapes | V1_Hourly Wind Shapes
2023-09-27 | V1_ Heat rates | V1_Thermal Plant Data V1_ Cycling Data (Start costs, other) V1_ Min up/down time V1_ Ramp Rates |  | V1_ Heat rates | [14 empty] | V1_Thermal Plant Data | V1_ Cycling Data (Start costs, other) | V1_ Min up/down time | V1_ Ramp Rates
2023-10-11 | V1_BTM PV Shapes and modeling methodology V1_FOR | V1_ Heat rates |  | V1_BTM PV Shapes and modeling methodology | V1_FOR | [13 empty] | V1_ Heat rates
2023-10-25 | V1_Path definitions/ratings - WECC Paths V1_Review all interfaces - Non WECC Paths | V1_BTM PV Shapes and modeling methodology V1_FOR |  | V1_Path definitions/ratings - WECC Paths | V1_Review all interfaces - Non WECC Paths | [13 empty] | V1_BTM PV Shapes and modeling methodology | V1_FOR
2023-11-08 | V1_Transmission Nomograms V1_EPE and TEPC load and generation balance nomograms | V1_Path definitions/ratings - WECC Paths V1_Review all interfaces - Non WECC Paths |  | V1_Transmission Nomograms | V1_EPE and TEPC load and generation balance nomograms | [13 empty] | V1_Path definitions/ratings - WECC Paths | V1_Review all interfaces - Non WECC Paths
2023-11-22 | V1_Wheeling Rates (from utility tariffs) | V1_Transmission Nomograms V1_EPE and TEPC load and generation balance nomograms |  | V1_Wheeling Rates (from utility tariffs) | [14 empty] | V1_Transmission Nomograms | V1_EPE and TEPC load and generation balance nomograms
2023-12-06 | V1_Wheeling Rates (from utility tariffs) | [9 empty] | 4 Weeks1: V1_Wheeling Rates (from utility tariffs)
2023-12-20 | V1_Deflator/Inflator rates V2_ Natural Gas Prices V2_ Coal Prices V2_ Uranium Prices V2_ Other fuels Prices V2_Deflator/Inflator rates | V1_Wheeling Rates (from utility tariffs) |  | V1_Deflator/Inflator rates | V2_ Natural Gas Prices | V2_ Coal Prices | V2_ Uranium Prices | V2_ Other fuels Prices | V2_Deflator/Inflator rates | [9 empty] | V1_Wheeling Rates (from utility tariffs)
2024-01-03 | V2_Path definitions/ratings - WECC Paths V1_Deflator/Inflator rates V2_ Natural Gas Prices V2_ Coal Prices V2_ Uranium Prices |  |  | V2_Path definitions/ratings - WECC Paths | [6 empty] | 4 Weeks1: V1_Deflator/Inflator rates; 4 Weeks2: V2_ Natural Gas Prices; 4 Weeks3: V2_ Coal Prices; 4 Weeks4: V2_ Uranium Prices
2024-01-17 | V2_CO2 prices California V2_CO2 prices Washington Oregon V2_CO2 prices BC and Alberta V2_Path definitions/ratings - WECC Paths | V1_Deflator/Inflator rates |  | V2_CO2 prices California | V2_CO2 prices Washington Oregon | V2_CO2 prices BC and Alberta |  |  |  |  | 4 Weeks1: V2_Path definitions/ratings - WECC Paths | V1_Deflator/Inflator rates
2024-01-31 | V1_Variable O&M for all thermal generator types V1_Variable O&M for all Non-thermal generator types V2_BC Hydro Data V2_Path definitions/ratings - WECC Paths |  |  | V1_Variable O&M for all thermal generator types | V1_Variable O&M for all Non-thermal generator types | V2_BC Hydro Data |  |  |  |  | 6 Weeks1: V2_Path definitions/ratings - WECC Paths
2024-02-14 | V1_Dispatch price for wind, solar, and hydro (Also called oportunity cost) V2_Load Shapes | V1_Variable O&M for all thermal generator types V1_Variable O&M for all Non-thermal generator types |  | V1_Dispatch price for wind, solar, and hydro (Also called oportunity cost) | V2_Load Shapes | [14 empty] | V1_Variable O&M for all thermal generator types | V1_Variable O&M for all Non-thermal generator types
2024-02-28 | V2_Load Shapes | V1_Dispatch price for wind, solar, and hydro (Also called oportunity cost) | [8 empty] | 4 Weeks1: V2_Load Shapes | V1_Dispatch price for wind, solar, and hydro (Also called oportunity cost)
2024-03-13 | V2_ Demand Response Shapes V2_ Energy Efficiency V2_Load-Following and Regulation reserve calculations |  |  | V2_ Demand Response Shapes | V2_ Energy Efficiency | V2_Load-Following and Regulation reserve calculations
2024-03-27 | V1_Maintenance Schedule V2_ Electric Vehicle loads V2_ Electrification Loads V2_ BTM PV V2_ BTM Storage V2_Maintenance Schedule V2_Load-Following and Regulation reserve calculations |  |  | V1_Maintenance Schedule | V2_ Electric Vehicle loads | V2_ Electrification Loads | V2_ BTM PV | V2_ BTM Storage | V2_Maintenance Schedule |  | 4 Weeks1: V2_Load-Following and Regulation reserve calculations
2024-04-10 | V2_Hourly Utility Scale Solar shapes V2_Hourly Wind Shapes V2_BTM PV Shapes and modeling methodology V2_Load-Following and Regulation reserve calculations | V1_Maintenance Schedule |  | V2_Hourly Utility Scale Solar shapes | V2_Hourly Wind Shapes | V2_BTM PV Shapes and modeling methodology |  |  |  |  | 6 Weeks1: V2_Load-Following and Regulation reserve calculations | V1_Maintenance Schedule
2024-04-24
2024-05-08
2024-05-22
2024-06-05
2024-06-19
2024-07-03
2024-07-17
2024-07-31
2024-08-14
2024-08-28
2024-09-11
2024-09-25
2024-10-09
2024-10-23
2024-11-06
2024-11-20
2024-12-04
2024-12-18

## Other Data Schedule_NoNone (hidden)
Version | Version Other Data Items | Other Data Items | Original Index | Current Data Used | Data Availability - Date | Last Updated | Decision/Date (when we made the decision) | Action/Notes | Contacts | Incremental Updates | Implementation Schedule ADS-Begin | Implementation Schedule ADS-End | Days from start | 2023-01-01 | Implementatin Number of Days | 2024-01-31 | 45322
V1 | V1_BC Hydro Data | BC Hydro Data | 9 |  |  | Older vintage | Update if available, ask BC Hydro for update | Recalculation - Taylor dispatch to support new load data for 2023 and 2024. Ask Nathalie Voisin and PNNL. If we can define a process, we can ask hitachi to make GV enhancement |  | Ask BC for updates, PNNL, Nathalie Voisin | 2023-05-24 | 2023-06-07 | 143 | 2023-05-24 | 14
V1 | V1_Load Shapes | Load Shapes | 10 | 2018 shape and 2022 L&R monthly peak and energy | March-April | 2022-04-01 | Update load forecast | Still using 2018 base year, but updated based on latest L&R, peak and energy |  |  | 2023-06-07 | 2023-07-12 | 157 | 2023-06-07 | 35
V1 | V1_ Demand Response Shapes | Demand Response Shapes | 11 | LBNL based off available DR from L&R and LMPs form 2032 ADS run |  | 2022-08-01 | Update at end of build | May need to have GV to dispatch |  |  | 2023-07-12 | 2023-07-19 | 192 | 2023-07-12 | 7
V1 | V1_ Energy Efficiency | Energy Efficiency | 12 | Not used in 2032 |  | None | Update as needed, if available | Built into the load forecast, AAEE for CA, need CEC data |  |  | 2023-07-12 | 2023-07-19 | 192 | 2023-07-12 | 7
V1 | V1_ Electric Vehicle loads | Electric Vehicle loads | 14 | N/A |  | None | Updated if available | For CA layer in unique load shape as needed. Ask CA what they want to do for 2023. V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2023-07-12 | 2023-07-19 | 192 | 2023-07-12 | 7
V1 | V1_ Electrification Loads | Electrification Loads | 15 | N/A |  | None | Updated if available | For CA layer in unique load shape as needed. V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2023-07-12 | 2023-07-19 | 192 | 2023-07-12 | 7
V1 | V1_Transmission Contingencies | Transmission Contingencies | 4 | N/A |  | None | Discuss Further | TBD |  |  | 2023-07-19 | 2023-08-02 | 199 | 2023-07-19 | 14
V1 | V1_Phase Shifter Transformers - How to treat, and review | Phase Shifter Transformers - How to treat, and review | 40 |  |  |  | Discuss Further |  |  |  | 2023-07-19 | 2023-08-02 | 199 | 2023-07-19 | 14
V1 | V1_ BTM PV | BTM PV | 16 |  |  |  | Updated if available | V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2023-08-02 | 2023-08-16 | 213 | 2023-08-02 | 14
V1 | V1_ BTM Storage | BTM Storage | 17 |  |  |  | Updated if available | V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2023-08-02 | 2023-08-16 | 213 | 2023-08-02 | 14
V1 | V1_Hourly Wind Shapes | Hourly Wind Shapes | 18 | NREL |  | 2022-05-01 | Update if needed, planned resources | review data quality with NREL to see if there is updated data. This is for new or units with missing data. V2 incremental changes | Anthony Lopez, Greg Brinkeman | Update with Wind Toolkit Data, test with units we have had issues with | 2023-08-16 | 2023-09-13 | 227 | 2023-08-16 | 28
V1 | V1_Hourly Utility Scale Solar shapes | Hourly Utility Scale Solar shapes | 19 | NREL |  | 2022-05-01 | Add shapes for new planned resources | Incemental updates for V1 and V2 |  |  | 2023-08-16 | 2023-09-13 | 227 | 2023-08-16 | 28
V1 | V1_Thermal Plant Data | Thermal Plant Data | 21 | [7 empty] | 2023-09-13 | 2023-09-27 | 255 | 2023-09-13 | 14
V1 | V1_ Cycling Data (Start costs, other) | Cycling Data (Start costs, other) | 22 | 2020 Intertek Report |  | 2020-05-01 | Check with Intertek on frequency of updates | Check with Intertek, only do once, either V1 or V2 |  |  | 2023-09-13 | 2023-09-27 | 255 | 2023-09-13 | 14
V1 | V1_ Min up/down time | Min up/down time | 23 |  |  | 2020-05-01 | Check with Intertek on frequency of updates |  |  |  | 2023-09-13 | 2023-09-27 | 255 | 2023-09-13 | 14
V1 | V1_ Ramp Rates | Ramp Rates | 24 | 2020 Intertek Report |  | 2020-05-01 | Check with Intertek on frequency of updates |  |  |  | 2023-09-13 | 2023-09-27 | 255 | 2023-09-13 | 14
V1 | V1_ Heat rates | Heat rates | 25 | CEC and Kevin Harris analysis of CEMS data |  | 2020-06-01 | Check with Intertek on frequency of updates |  |  |  | 2023-09-27 | 2023-10-11 | 269 | 2023-09-27 | 14
V1 | V1_BTM PV Shapes and modeling methodology | BTM PV Shapes and modeling methodology | 20 | NREL |  | 2022-05-01 | Needs to be evaluated. Update magitude, not the shapes | County by utility bus vs Area granularity |  |  | 2023-10-11 | 2023-10-25 | 283 | 2023-10-11 | 14
V1 | V1_FOR | FOR | 27 | GADS pc-GAR |  | 2022-01-01 | Update, GADS PCgar | GADS pcgar |  |  | 2023-10-11 | 2023-10-25 | 283 | 2023-10-11 | 14
V1 | V1_Path definitions/ratings - WECC Paths | Path definitions/ratings - WECC Paths | 1 | 2022 Path Rating Catalog | April | 2022-04-01 | Update with Path Rating Catalog | Include any Phase 3, maybe 2B transmision project |  | Minor-incremental updates from 2023 PRC | 2023-10-25 | 2023-11-08 | 297 | 2023-10-25 | 14
V1 | V1_Review all interfaces - Non WECC Paths | Review all interfaces - Non WECC Paths | 2 |  |  |  | Review definitions - working session PCDS | Review definitions |  |  | 2023-10-25 | 2023-11-08 | 297 | 2023-10-25 | 14
V1 | V1_Transmission Nomograms | Transmission Nomograms | 3 | BPA provided Path 8 nomogram |  |  | Discuss Further- ask for updates | ask TEPC and EPE for updates |  | Minor - updates to nomogram | 2023-11-08 | 2023-11-22 | 311 | 2023-11-08 | 14
V1 | V1_EPE and TEPC load and generation balance nomograms | EPE and TEPC load and generation balance nomograms | 5 | Generation from L&R and confirmation from WestConnect |  |  | Update - 3/15/2023 | Verify proper modeling, send to EPE and TEPC, review list of supply for feedback |  | Minor - updates to nomogram | 2023-11-08 | 2023-11-22 | 311 | 2023-11-08 | 14
V1 | V1_Wheeling Rates (from utility tariffs) | Wheeling Rates (from utility tariffs) | 6 | Utility OASIS data |  | 2021-12-01 | Check and Update as necessary |  |  |  | 2023-11-22 | 2023-12-20 | 325 | 2023-11-22 | 28
V2 | V2_ Natural Gas Prices | Natural Gas Prices | 28 | CEC 2021 IEPR | December | 2022-02-01 | Update | Make change case available if data is available for V1 |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V2 | V2_ Coal Prices | Coal Prices | 29 | Inflated 2030 ADS prices |  | 2022-02-01 | Update |  |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V2 | V2_ Uranium Prices | Uranium Prices | 30 | 2022 Price |  | 2022-02-01 | Update |  |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V2 | V2_ Other fuels Prices | Other fuels Prices | 31 | Inflated 2030 ADS prices |  | 2022-02-01 | Update |  |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V2 | V2_Deflator/Inflator rates | Deflator/Inflator rates | 37 | Moody's inflator |  | 2022-02-01 | Update | Ask CEC if deflator series changes every year, otherwise just do once |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V1 | V1_Deflator/Inflator rates | Deflator/Inflator rates | 77 | Moody's inflator |  | 44593 | Update | Ask CEC if deflator series changes every year, otherwise just do once |  |  | 2023-12-20 | 2024-01-17 | 353 | 2023-12-20 | 28
V2 | V2_Path definitions/ratings - WECC Paths | Path definitions/ratings - WECC Paths | 41 | 2022 Path Rating Catalog | April | 44652 | Update with Path Rating Catalog | Include any Phase 3, maybe 2B transmision project |  | Minor-incremental updates from 2023 PRC | 2024-01-03 | 2024-02-14 | 367 | 2024-01-03 | 42
V2 | V2_CO2 prices California | CO2 prices California | 32 | CEC 2021 IEPR | December | 2022-04-01 | Update |  |  |  | 2024-01-17 | 2024-01-31 | 381 | 2024-01-17 | 14
V2 | V2_CO2 prices Washington Oregon | CO2 prices Washington Oregon | 33 |  |  | NA | Update, reach out to BPA |  |  |  | 2024-01-17 | 2024-01-31 | 381 | 2024-01-17 | 14
V2 | V2_CO2 prices BC and Alberta | CO2 prices BC and Alberta | 34 |  |  |  | Update |  |  |  | 2024-01-17 | 2024-01-31 | 381 | 2024-01-17 | 14
V2 | V2_BC Hydro Data | BC Hydro Data | 49 |  |  | Older vintage | Update if available, ask BC Hydro for update | Recalculation - Taylor dispatch to support new load data for 2023 and 2024. Ask Nathalie Voisin and PNNL. If we can define a process, we can ask hitachi to make GV enhancement |  | Ask BC for updates, PNNL, Nathalie Voisin | 2024-01-31 | 2024-02-14 | 395 | 2024-01-31 | 14
V1 | V1_Variable O&M for all thermal generator types | Variable O&M for all thermal generator types | 66 |  |  |  | Check with Intertek |  |  |  | 2024-01-31 | 2024-02-14 | 395 | 2024-01-31 | 14
V1 | V1_Variable O&M for all Non-thermal generator types | Variable O&M for all Non-thermal generator types | 75 | INTERTEK Cycleing Cost Report |  | 44440 | Update |  |  |  | 2024-01-31 | 2024-02-14 | 395 | 2024-01-31 | 14
V2 | V2_Load Shapes | Load Shapes | 50 | 2018 shape and 2022 L&R monthly peak and energy | March-April | 44652 | Update load forecast | Still using 2018 base year, but updated based on latest L&R, peak and energy |  |  | 2024-02-14 | 2024-03-13 | 409 | 2024-02-14 | 28
V1 | V1_Dispatch price for wind, solar, and hydro (Also called oportunity cost) | Dispatch price for wind, solar, and hydro (Also called oportunity cost) | 76 | INTERTEK Cycleing Cost Report |  | 44440 | Update |  |  |  | 2024-02-14 | 2024-02-28 | 409 | 2024-02-14 | 14
V2 | V2_Load-Following and Regulation reserve calculations | Load-Following and Regulation reserve calculations | 38 | PNNL |  | 2023-03-01 |  | PNNL |  |  | 2024-03-13 | 2024-04-24 | 437 | 2024-03-13 | 42
V2 | V2_ Demand Response Shapes | Demand Response Shapes | 51 | LBNL based off available DR from L&R and LMPs form 2032 ADS run |  | 44774 | Update at end of build | May need to have GV to dispatch |  |  | 2024-03-13 | 2024-03-27 | 437 | 2024-03-13 | 14
V2 | V2_ Energy Efficiency | Energy Efficiency | 52 | Not used in 2032 |  | None | Update as needed, if available | Built into the load forecast, AAEE for CA, need CEC data |  |  | 2024-03-13 | 2024-03-27 | 437 | 2024-03-13 | 14
V2 | V2_Maintenance Schedule | Maintenance Schedule | 39 | WECC |  | 2022-07-01 | Update |  |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V2 | V2_ Electric Vehicle loads | Electric Vehicle loads | 54 | N/A |  | None | Updated if available | For CA layer in unique load shape as needed. Ask CA what they want to do for 2023. V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V2 | V2_ Electrification Loads | Electrification Loads | 55 | N/A |  | None | Updated if available | For CA layer in unique load shape as needed. V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V2 | V2_ BTM PV | BTM PV | 56 |  |  |  | Updated if available | V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V2 | V2_ BTM Storage | BTM Storage | 57 |  |  |  | Updated if available | V1 develop methodology and shape. V2, only change new peak/energy |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V1 | V1_Maintenance Schedule | Maintenance Schedule | 79 | WECC |  | 44743 | Update |  |  |  | 2024-03-27 | 2024-04-10 | 451 | 2024-03-27 | 14
V2 | V2_Hourly Wind Shapes | Hourly Wind Shapes | 58 | NREL |  | 44682 | Update if needed, planned resources | review data quality with NREL to see if there is updated data. This is for new or units with missing data. V2 incremental changes | Anthony Lopez, Greg Brinkeman | Update with Wind Toolkit Data, test with units we have had issues with | 2024-04-10 | 2024-04-24 | 465 | 2024-04-10 | 14
V2 | V2_Hourly Utility Scale Solar shapes | Hourly Utility Scale Solar shapes | 59 | NREL |  | 44682 | Add shapes for new planned resources | Incemental updates for V1 and V2 |  |  | 2024-04-10 | 2024-04-24 | 465 | 2024-04-10 | 14
V2 | V2_BTM PV Shapes and modeling methodology | BTM PV Shapes and modeling methodology | 60 | NREL |  | 44682 | Needs to be evaluated. Update magitude, not the shapes | County by utility bus vs Area granularity |  |  | 2024-04-10 | 2024-04-24 | 465 | 2024-04-10 | 14
Formulas:
Implementation Schedule ADS-Begin = XLOOKUP([Version Other Data Items],'PCDS Schedule'!B:B,'PCDS Schedule'!E:E)
Implementation Schedule ADS-End = XLOOKUP([Version Other Data Items],'PCDS Schedule'!B:B,'PCDS Schedule'!K:K)
Days from start = IFERROR(DAYS([Implementation Schedule ADS-Begin],P1),)
Implementatin Number of Days = IFERROR(DAYS([Implementation Schedule ADS-End],[Implementation Schedule ADS-Begin]),0)

## PCDS Schedule (hidden)
Version | Version Name | Weeks | Original Order | Present/Discussion meeting | HelperDiscussion | 4 weeks | Helper 4 weeks | 6 weeks | Helper 6 weeks | Approval meeting | HelperApproval |  |  | Discussion item(s) | Discussion Notes | Update for V1 | Update for V2 |  |  | Start | Duration | Duration + Start
V1 | V1_BC Hydro Data | 2 | 9 | 2023-05-24 | 45070_1 |  | _0 |  | _0 | 2023-06-07 | 45084_1 | 2023-06-07 | 2023-06-21 | BC Hydro Data | Update if available | X | X | 2023-01-09 | 135 | 2023-05-24 | 14 | 2023-06-07
V1 | V1_Load Shapes | 5 | 10 | 2023-06-07 | 45084_1 | 2023-06-21 | 45098_1 |  | _0 | 2023-07-12 | 45119_1 | 2023-06-21 | 2023-07-26 | Load Shapes | Update | X | X | 2023-01-10 | 148 | 2023-06-07 | 35 | 2023-07-12
V1 | V1_ Demand Response Shapes | 1 | 11 | 2023-07-12 | 45119_1 |  | _0 |  | _0 | 2023-07-19 | 45126_1 | 2023-07-26 | 2023-08-02 | Demand Response Shapes |  | X | X | 2023-01-11 | 182 | 2023-07-12 | 7 | 2023-07-19
V1 | V1_ Energy Efficiency | 1 | 12 | 2023-07-12 | 45119_2 |  | _0 |  | _0 | 2023-07-19 | 45126_2 | 2023-07-26 | 2023-08-02 | Energy Efficiency |  | X | X | 2023-01-12 | 181 | 2023-07-12 | 7 | 2023-07-19
V1 | V1_ Electric Vehicle loads | 1 | 14 | 2023-07-12 | 45119_3 |  | _0 |  | _0 | 2023-07-19 | 45126_3 | 2023-07-26 | 2023-08-02 | Electric Vehicle loads |  | X | X | 2023-01-14 | 179 | 2023-07-12 | 7 | 2023-07-19
V1 | V1_ Electrification Loads | 1 | 15 | 2023-07-12 | 45119_4 |  | _0 |  | _0 | 2023-07-19 | 45126_4 | 2023-07-26 | 2023-08-02 | Electrification Loads |  | X | X | 2023-01-15 | 178 | 2023-07-12 | 7 | 2023-07-19
V1 | V1_Transmission Contingencies | 2 | 5 | 2023-07-19 | 45126_1 |  | _0 |  | _0 | 2023-08-02 | 45140_1 | 2023-07-05 | 2023-07-19 | Transmission Contingencies | Discuss if/how we want to incorporate TX contingencies | X |  | 2023-01-05 | 195 | 2023-07-19 | 14 | 2023-08-02
V1 | V1_Phase Shifter Transformers - How to treat, and review | 2 | 40 | 2023-07-19 | 45126_2 |  | _0 |  | _0 | 2023-08-02 | 45140_2 | 2023-07-05 | 2023-07-19 | Phase Shifter Transformers - How to treat, and review | Discuss if want to review operation of phase shifter |  |  | 2023-02-09 | 160 | 2023-07-19 | 14 | 2023-08-02
V1 | V1_ BTM PV | 2 | 16 | 2023-08-02 | 45140_1 |  | _0 |  | _0 | 2023-08-16 | 45154_1 | 2023-07-19 | 2023-08-02 | BTM PV |  | X | X | 2023-01-16 | 198 | 2023-08-02 | 14 | 2023-08-16
V1 | V1_ BTM Storage | 2 | 17 | 2023-08-02 | 45140_2 |  | _0 |  | _0 | 2023-08-16 | 45154_2 | 2023-07-19 | 2023-08-02 | BTM Storage |  | X | X | 2023-01-17 | 197 | 2023-08-02 | 14 | 2023-08-16
V1 | V1_Hourly Utility Scale Solar shapes | 4 | 18 | 2023-08-16 | 45154_1 | 2023-08-30 | 45168_1 |  | _0 | 2023-09-13 | 45182_1 | 2023-08-02 | 2023-08-30 | Hourly Utility Scale Solar shapes | Update | X | X | 2023-01-18 | 210 | 2023-08-16 | 28 | 2023-09-13
V1 | V1_Hourly Wind Shapes | 4 | 19 | 2023-08-16 | 45154_2 | 2023-08-30 | 45168_2 |  | _0 | 2023-09-13 | 45182_2 | 2023-08-02 | 2023-08-30 | Hourly Wind Shapes | Update | X | X | 2023-01-19 | 209 | 2023-08-16 | 28 | 2023-09-13
V1 | V1_Thermal Plant Data | 2 | 21 | 2023-09-13 | 45182_1 |  | _0 |  | _0 | 2023-09-27 | 45196_1 | 2023-08-30 | 2023-09-13 | Thermal Plant Data | Check with Intertek on frequency of updates. Thermal plant data (cycling, min/max up/down times ramp rates, heat rates | X |  | 2023-01-21 | 235 | 2023-09-13 | 14 | 2023-09-27
V1 | V1_ Cycling Data (Start costs, other) | 2 | 22 | 2023-09-13 | 45182_2 |  | _0 |  | _0 | 2023-09-27 | 45196_2 | 2023-08-30 | 2023-09-13 | Cycling Data (Start costs, other) |  |  |  | 2023-01-22 | 234 | 2023-09-13 | 14 | 2023-09-27
V1 | V1_ Min up/down time | 2 | 23 | 2023-09-13 | 45182_3 |  | _0 |  | _0 | 2023-09-27 | 45196_3 | 2023-08-30 | 2023-09-13 | Min up/down time |  |  |  | 2023-01-23 | 233 | 2023-09-13 | 14 | 2023-09-27
V1 | V1_ Ramp Rates | 2 | 24 | 2023-09-13 | 45182_4 |  | _0 |  | _0 | 2023-09-27 | 45196_4 | 2023-08-30 | 2023-09-13 | Ramp Rates |  |  |  | 2023-01-24 | 232 | 2023-09-13 | 14 | 2023-09-27
V1 | V1_ Heat rates | 2 | 25 | 2023-09-27 | 45196_1 |  | _0 |  | _0 | 2023-10-11 | 45210_1 | 2023-09-13 | 2023-09-27 | Heat rates |  |  |  | 2023-01-25 | 245 | 2023-09-27 | 14 | 2023-10-11
V1 | V1_BTM PV Shapes and modeling methodology | 2 | 20 | 2023-10-11 | 45210_1 |  | _0 |  | _0 | 2023-10-25 | 45224_1 | 2023-09-27 | 2023-10-11 | BTM PV Shapes and modeling methodology | Update | X | X | 2023-01-20 | 264 | 2023-10-11 | 14 | 2023-10-25
V1 | V1_FOR | 2 | 27 | 2023-10-11 | 45210_2 |  | _0 |  | _0 | 2023-10-25 | 45224_2 | 2023-09-27 | 2023-10-11 | FOR |  | X |  | 2023-01-27 | 257 | 2023-10-11 | 14 | 2023-10-25
V1 | V1_Path definitions/ratings - WECC Paths | 2 | 1 | 2023-10-25 | 45224_1 |  | _0 |  | _0 | 2023-11-08 | 45238_1 | 2023-10-11 | 2023-10-25 | Path definitions/ratings - WECC Paths | Update WECC Path Ratings with 2022 for V1, 2023 for V2 | X | X | 2023-01-01 | 297 | 2023-10-25 | 14 | 2023-11-08
V1 | V1_Review all interfaces - Non WECC Paths | 2 | 2 | 2023-10-25 | 45224_2 |  | _0 |  | _0 | 2023-11-08 | 45238_2 | 2023-10-11 | 2023-10-25 | Review all interfaces - Non WECC Paths | Review non-WECC Interfaces, do we need/want them | X |  | 2023-01-02 | 296 | 2023-10-25 | 14 | 2023-11-08
V1 | V1_Transmission Nomograms | 2 | 3 | 2023-11-08 | 45238_1 |  | _0 |  | _0 | 2023-11-22 | 45252_1 | 2023-10-25 | 2023-11-08 | Transmission Nomograms | Ask for updates | X |  | 2023-01-03 | 309 | 2023-11-08 | 14 | 2023-11-22
V1 | V1_EPE and TEPC load and generation balance nomograms | 2 | 4 | 2023-11-08 | 45238_2 |  | _0 |  | _0 | 2023-11-22 | 45252_2 | 2023-10-25 | 2023-11-08 | EPE and TEPC load and generation balance nomograms | Check with EPE, TEPC, Path for updates | X |  | 2023-01-04 | 308 | 2023-11-08 | 14 | 2023-11-22
V1 | V1_Wheeling Rates (from utility tariffs) | 4 | 6 | 2023-11-22 | 45252_1 | 2023-12-06 | 45266_1 |  | _0 | 2023-12-20 | 45280_1 | 2023-11-08 | 2023-12-06 | Wheeling Rates (from utility tariffs) | Update with OASIS Data | X |  | 2023-01-06 | 320 | 2023-11-22 | 28 | 2023-12-20
V1 | V1_Deflator/Inflator rates | 4 | 37 | 2023-12-20 | 45280_1 | 2024-01-03 | 45294_1 |  | _0 | 2024-01-17 | 45308_1 | 2023-12-06 | 2024-01-03 | Deflator/Inflator rates |  | X | X | 2023-02-06 | 317 | 2023-12-20 | 28 | 2024-01-17
V2 | V2_ Natural Gas Prices | 4 | 68 | 2023-12-20 | 45280_2 | 2024-01-03 | 45294_2 |  | _0 | 2024-01-17 |  | 2023-12-06 | 2024-01-03 | Natural Gas Prices |  |  |  | 2023-03-09 | 286 | 2023-12-20 | 28 | 2024-01-17
V2 | V2_ Coal Prices | 4 | 69 | 2023-12-20 | 45280_3 | 2024-01-03 | 45294_3 |  | _0 | 2024-01-17 |  | 2023-12-06 | 2024-01-03 | Coal Prices |  |  |  | 2023-03-10 | 285 | 2023-12-20 | 28 | 2024-01-17
V2 | V2_ Uranium Prices | 4 | 70 | 2023-12-20 | 45280_4 | 2024-01-03 | 45294_4 |  | _0 | 2024-01-17 |  | 2023-12-06 | 2024-01-03 | Uranium Prices |  |  |  | 2023-03-11 | 284 | 2023-12-20 | 28 | 2024-01-17
V2 | V2_ Other fuels Prices | 4 | 71 | 2023-12-20 | 45280_5 | 2024-01-03 | 45294_5 |  | _0 | 2024-01-17 |  | 2023-12-06 | 2024-01-03 | Other fuels Prices |  |  |  | 2023-03-12 | 283 | 2023-12-20 | 28 | 2024-01-17
V2 | V2_Deflator/Inflator rates | 4 | 77 | 2023-12-20 | 45280_6 | 2024-01-03 | 45294_6 |  | _0 | 2024-01-17 |  | 2023-12-06 | 2024-01-03 | Deflator/Inflator rates |  |  |  | 2023-03-18 | 277 | 2023-12-20 | 28 | 2024-01-17
V2 | V2_Path definitions/ratings - WECC Paths | 6 | 41 | 2024-01-03 | 45294_1 | 2024-01-17 | 45308_1 | 2024-01-31 | 45322_1 | 2024-02-14 |  | 2023-12-20 | 2024-01-31 | Path definitions/ratings - WECC Paths | Update WECC Path Ratings with 2022 for V1, 2023 for V2 |  |  | 2023-02-10 | 327 | 2024-01-03 | 42 | 2024-02-14
V2 | V2_CO2 prices California | 2 | 72 | 2024-01-17 | 45308_1 |  | _0 |  | _0 | 2024-01-31 |  | 2024-01-03 | 2024-01-17 | CO2 prices California |  |  |  | 2023-03-13 | 310 | 2024-01-17 | 14 | 2024-01-31
V2 | V2_CO2 prices Washington Oregon | 2 | 73 | 2024-01-17 | 45308_2 |  | _0 |  | _0 | 2024-01-31 |  | 2024-01-03 | 2024-01-17 | CO2 prices Washington Oregon |  |  |  | 2023-03-14 | 309 | 2024-01-17 | 14 | 2024-01-31
V2 | V2_CO2 prices BC and Alberta | 2 | 74 | 2024-01-17 | 45308_3 |  | _0 |  | _0 | 2024-01-31 |  | 2024-01-03 | 2024-01-17 | CO2 prices BC and Alberta |  |  |  | 2023-03-15 | 308 | 2024-01-17 | 14 | 2024-01-31
V1 | V1_Variable O&M for all thermal generator types | 2 | 26 | 2024-01-31 | 45322_1 |  | _0 |  | _0 | 2024-02-14 | 45336_2 | 2024-01-17 | 2024-01-31 | Variable O&M for all thermal generator types | Check with Intertek | X |  | 2023-01-26 | 370 | 2024-01-31 | 14 | 2024-02-14
V1 | V1_Variable O&M for all Non-thermal generator types | 2 | 35 | 2024-01-31 | 45322_2 |  | _0 |  | _0 | 2024-02-14 | 45336_3 | 2024-01-17 | 2024-01-31 | Variable O&M for all Non-thermal generator types |  | X |  | 2023-02-04 | 361 | 2024-01-31 | 14 | 2024-02-14
V2 | V2_BC Hydro Data | 2 | 49 | 2024-01-31 | 45322_3 |  | _0 |  | _0 | 2024-02-14 |  | 2024-01-17 | 2024-01-31 | BC Hydro Data | Update if available |  |  | 2023-02-18 | 347 | 2024-01-31 | 14 | 2024-02-14
V1 | V1_Dispatch price for wind, solar, and hydro (Also called oportunity cost) | 2 | 36 | 2024-02-14 | 45336_1 |  | _0 |  | _0 | 2024-02-28 | 45350_1 | 2024-01-31 | 2024-02-14 | Dispatch price for wind, solar, and hydro (Also called oportunity cost) |  | X |  | 2023-02-05 | 374 | 2024-02-14 | 14 | 2024-02-28
V2 | V2_Load Shapes | 4 | 50 | 2024-02-14 | 45336_2 | 2024-02-28 | 45350_1 |  | _0 | 2024-03-13 |  | 2024-01-31 | 2024-02-28 | Load Shapes | Update |  |  | 2023-02-19 | 360 | 2024-02-14 | 28 | 2024-03-13
V2 | V2_ Demand Response Shapes | 2 | 51 | 2024-03-13 | 45364_1 |  | _0 |  | _0 | 2024-03-27 |  | 2024-02-28 | 2024-03-13 | Demand Response Shapes |  |  |  | 2023-02-20 | 387 | 2024-03-13 | 14 | 2024-03-27
V2 | V2_ Energy Efficiency | 2 | 52 | 2024-03-13 | 45364_2 |  | _0 |  | _0 | 2024-03-27 |  | 2024-02-28 | 2024-03-13 | Energy Efficiency |  |  |  | 2023-02-21 | 386 | 2024-03-13 | 14 | 2024-03-27
V2 | V2_Load-Following and Regulation reserve calculations | 6 | 78 | 2024-03-13 | 45364_3 | 2024-03-27 | 45378_1 | 2024-04-10 | 45392_1 | 2024-04-24 |  | 2024-02-28 | 2024-04-10 | Load-Following and Regulation reserve calculations |  |  |  | 2023-03-19 | 360 | 2024-03-13 | 42 | 2024-04-24
V1 | V1_Maintenance Schedule | 2 | 39 | 2024-03-27 | 45378_1 |  | _0 |  | _0 | 2024-04-10 | 45392_1 | 2024-03-13 | 2024-03-27 | Maintenance Schedule |  | X | X | 2023-02-08 | 413 | 2024-03-27 | 14 | 2024-04-10
V2 | V2_ Electric Vehicle loads | 2 | 54 | 2024-03-27 | 45378_2 |  | _0 |  | _0 | 2024-04-10 |  | 2024-03-13 | 2024-03-27 | Electric Vehicle loads |  |  |  | 2023-02-23 | 398 | 2024-03-27 | 14 | 2024-04-10
V2 | V2_ Electrification Loads | 2 | 55 | 2024-03-27 | 45378_3 |  | _0 |  | _0 | 2024-04-10 |  | 2024-03-13 | 2024-03-27 | Electrification Loads |  |  |  | 2023-02-24 | 397 | 2024-03-27 | 14 | 2024-04-10
V2 | V2_ BTM PV | 2 | 56 | 2024-03-27 | 45378_4 |  | _0 |  | _0 | 2024-04-10 |  | 2024-03-13 | 2024-03-27 | BTM PV |  |  |  | 2023-02-25 | 396 | 2024-03-27 | 14 | 2024-04-10
V2 | V2_ BTM Storage | 2 | 57 | 2024-03-27 | 45378_5 |  | _0 |  | _0 | 2024-04-10 |  | 2024-03-13 | 2024-03-27 | BTM Storage |  |  |  | 2023-02-26 | 395 | 2024-03-27 | 14 | 2024-04-10
V2 | V2_Maintenance Schedule | 2 | 79 | 2024-03-27 | 45378_6 |  | _0 |  | _0 | 2024-04-10 |  | 2024-03-13 | 2024-03-27 | Maintenance Schedule |  |  |  | 2023-03-20 | 373 | 2024-03-27 | 14 | 2024-04-10
V2 | V2_Hourly Utility Scale Solar shapes | 2 | 58 | 2024-04-10 | 45392_1 |  | _0 |  | _0 | 2024-04-24 |  | 2024-03-27 | 2024-04-10 | Hourly Utility Scale Solar shapes | Update |  |  | 2023-02-27 | 408 | 2024-04-10 | 14 | 2024-04-24
V2 | V2_Hourly Wind Shapes | 2 | 59 | 2024-04-10 | 45392_2 |  | _0 |  | _0 | 2024-04-24 |  | 2024-03-27 | 2024-04-10 | Hourly Wind Shapes | Update |  |  | 2023-02-28 | 407 | 2024-04-10 | 14 | 2024-04-24
V2 | V2_BTM PV Shapes and modeling methodology | 2 | 60 | 2024-04-10 | 45392_3 |  | _0 |  | _0 | 2024-04-24 |  | 2024-03-27 | 2024-04-10 | BTM PV Shapes and modeling methodology | Update |  |  | 2023-03-01 | 406 | 2024-04-10 | 14 | 2024-04-24
V1 | V1_Coincident Energy Year Shapes | #VALUE! | 7 | None | None_1 |  | _0 |  | _0 | None | None_1 | #VALUE! | #VALUE! | Coincident Energy Year Shapes | No Change |  |  | 2023-01-07 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V1 | V1_Hydro Data (Weekly energy, min, max, etc.) | #VALUE! | 8 | None | None_2 |  | _0 |  | _0 | None | None_2 | #VALUE! | #VALUE! | Hydro Data (Weekly energy, min, max, etc.) | No Change |  |  | 2023-01-08 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V1 | V1_ Pump loads | #VALUE! | 13 | None | None_3 |  | _0 |  | _0 | None | None_3 | #VALUE! | #VALUE! | Pump loads |  | X | X | 2023-01-13 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V1 | V1_ Natural Gas Prices | #VALUE! | 28 | None | None_4 |  | _0 |  | _0 | None | None_4 | #VALUE! | #VALUE! | Natural Gas Prices |  |  | X | 2023-01-28 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V1 | V1_ Coal Prices | #VALUE! | 29 | None | None_5 |  | _0 |  | _0 | None | None_5 | #VALUE! | #VALUE! | Coal Prices |  |  | X | 2023-01-29 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V1 | V1_ Uranium Prices | #VALUE! | 30 | None | None_6 |  | _0 |  | _0 | None | None_6 | #VALUE! | #VALUE! | Uranium Prices |  |  | X | 2023-01-30 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V1 | V1_ Other fuels Prices | #VALUE! | 31 | None | None_7 |  | _0 |  | _0 | None | None_7 | #VALUE! | #VALUE! | Other fuels Prices |  |  | X | 2023-01-31 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V1 | V1_CO2 prices California | #VALUE! | 32 | None | None_8 |  | _0 |  | _0 | None | None_8 | #VALUE! | #VALUE! | CO2 prices California |  |  | X | 2023-02-01 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V1 | V1_CO2 prices Washington Oregon | #VALUE! | 33 | None | None_9 |  | _0 |  | _0 | None | None_9 | #VALUE! | #VALUE! | CO2 prices Washington Oregon |  |  | X | 2023-02-02 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V1 | V1_CO2 prices BC and Alberta | #VALUE! | 34 | None | None_10 |  | _0 |  | _0 | None | None_10 | #VALUE! | #VALUE! | CO2 prices BC and Alberta |  |  | X | 2023-02-03 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V1 | V1_Load-Following and Regulation reserve calculations | #VALUE! | 38 | None | None_11 |  | _0 |  | _0 | None | None_11 | #VALUE! | #VALUE! | Load-Following and Regulation reserve calculations |  |  | X | 2023-02-07 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_Review all interfaces - Non WECC Paths | #VALUE! | 42 | None | None_12 |  | _0 |  | _0 | None |  |  |  | Review all interfaces - Non WECC Paths | Review non-WECC Interfaces, do we need/want them |  |  | 2023-02-11 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_Transmission Nomograms | #VALUE! | 43 | None | None_13 |  | _0 |  | _0 | None |  |  |  | Transmission Nomograms | Ask for updates |  |  | 2023-02-12 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_EPE and TEPC load and generation balance nomograms | #VALUE! | 44 | None | None_14 |  | _0 |  |  | None |  |  |  | EPE and TEPC load and generation balance nomograms | Check with EPE, TEPC, Path for updates |  |  | 2023-02-13 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_Transmission Contingencies | #VALUE! | 45 | None | None_15 |  | _0 |  | _0 | None |  |  |  | Transmission Contingencies | Discuss if/how we want to incorporate TX contingencies |  |  | 2023-02-14 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_Wheeling Rates (from utility tariffs) | #VALUE! | 46 | None | None_16 |  | _0 |  | _0 | None |  |  |  | Wheeling Rates (from utility tariffs) | Update with OASIS Data |  |  | 2023-02-15 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_Coincident Energy Year Shapes | #VALUE! | 47 | None | None_17 |  | _0 |  | _0 | None |  |  |  | Coincident Energy Year Shapes | No Change |  |  | 2023-02-16 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_Hydro Data (Weekly energy, min, max, etc.) | #VALUE! | 48 | None | None_18 |  | _0 |  | _0 | None |  |  |  | Hydro Data (Weekly energy, min, max, etc.) | No Change |  |  | 2023-02-17 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_ Pump loads | #VALUE! | 53 | None | None_19 |  | _0 |  | _0 | None |  |  |  | Pump loads |  |  |  | 2023-02-22 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_Thermal Plant Data | #VALUE! | 61 | None | None_20 |  | _0 |  | _0 | None |  |  |  | Thermal Plant Data | Check with Intertek on frequency of updates. Thermal plant data (cycling, min/max up/down times ramp rates, heat rates |  |  | 2023-03-02 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_ Cycling Data (Start costs, other) | #VALUE! | 62 | None | None_21 |  | _0 |  | _0 | None |  |  |  | Cycling Data (Start costs, other) |  |  |  | 2023-03-03 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_ Min up/down time | #VALUE! | 63 | None | None_22 |  | _0 |  | _0 | None |  |  |  | Min up/down time |  |  |  | 2023-03-04 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_ Ramp Rates | #VALUE! | 64 | None | None_23 |  | _0 |  | _0 | None |  |  |  | Ramp Rates |  |  |  | 2023-03-05 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_ Heat rates | #VALUE! | 65 | None | None_24 |  | _0 |  | _0 | None |  |  |  | Heat rates |  |  |  | 2023-03-06 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_Variable O&M for all thermal generator types | #VALUE! | 66 | None | None_25 |  | _0 |  | _0 | None |  |  |  | Variable O&M for all thermal generator types | Check with Intertek |  |  | 2023-03-07 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_FOR | #VALUE! | 67 | None | None_26 |  | _0 |  | _0 | None |  |  |  | FOR |  |  |  | 2023-03-08 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_Variable O&M for all Non-thermal generator types | #VALUE! | 75 | None | None_27 |  | _0 |  | _0 | None |  |  |  | Variable O&M for all Non-thermal generator types |  |  |  | 2023-03-16 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_Dispatch price for wind, solar, and hydro (Also called oportunity cost) | #VALUE! | 76 | None | None_28 |  | _0 |  | _0 | None |  |  |  | Dispatch price for wind, solar, and hydro (Also called oportunity cost) |  |  |  | 2023-03-17 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
V2 | V2_Phase Shifter Transformers - How to treat, and review | #VALUE! | 80 | None | None_29 |  | _0 |  | _0 | None |  |  |  | Phase Shifter Transformers - How to treat, and review | Discuss if want to review operation of phase shifter |  |  | 2023-03-21 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Formulas:
Duration = DAYS([Approval meeting],[Present/Discussion meeting])
Duration + Start = [Duration]+[Start]