## Other Data Schedule
Other Data Items | V1 (March, 2034) V2 (July, 2024) | Current Data Used | Data Availability - Date | Last Updated | Decision/Date(when we made the decision) | V1 - Implementation Schedule ADS-Begin | V1 - Implementation Schedule ADS-End | V2 - Implementation Schedule ADS-Begin | V2 - Implementation Schedule ADS-End | V1 Number of days | V2 Number of days | Incremental Updates | Notes |  | 2023-01-01 | V1 Number of Days | V1-V2 Number of Days | V2 Number of Days | 44927 | 45010
Path definitions/ratings |  | 2022 Path Rating Catalog | April | 2022-04-01 | Update | 2023-09-01 | 2024-01-01 | 2024-03-01 | 2024-04-30 | 122 | 60 | Minor-incremental updates from 2023 PRC | Include any Phase 3, maybe 2B transmision project | 243 | 2023-09-01 | 122 | 60 | 60
Review all interfaces | [5 empty] | 2023-05-01 | 2023-09-01 | None | None
Transmission Nomograms |  | BPA provided Path 8 nomogram |  |  | Discuss Further- ask TEPC and EPE for updates | 2023-12-01 | 2024-02-01 | None | None | 62 | #VALUE! | Minor - updates to nomogram | ask TEPC and EPE for updates | 334 | 2023-12-01 | 62 | #VALUE! | #VALUE!
Transmission Contingencies |  | N/A |  | None | Discuss Further |  |  |  |  | 0 | 0 |  | TBD | -44927 | 0 | 0 | 0 | 0
EPE and TEPC load and generation balance nomograms |  | Generation from L&R and confirmation from WestConnect |  |  | Update - 3/15/2023 | 2023-12-01 | 2024-02-01 | None | None | 62 | #VALUE! | Minor - updates to nomogram | Verify proper modeling, send to EPE and TEPC, review list of supply for feedback | 334 | 2023-12-01 | 62 | #VALUE! | #VALUE!
Wheeling Rates (from utility tariffs) |  | Utility OASIS data |  | 2021-12-01 | Check and Update as necessary | 2023-12-01 | 2024-01-01 | None | None | 31 | #VALUE! |  |  | 334 | 2023-12-01 | 31 | #VALUE! | #VALUE!
Coincident Energy Year Shapes |  | Year 2018 |  | 2021-07-01 | No change for this cycle | None | None | None | None | #VALUE! | #VALUE! |  | Keep 2018 as the year | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Hydro Data (Weekly energy, min, max, etc.) |  | Actual 2018 data and BPA models using 2018 as base |  | 2022-04-01 | No change for this cycle | None | None | None | None | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
BC Hydro Data |  |  |  | Older vintage | Update if available, ask BC Hydro for update | 2023-05-01 | 2023-08-01 | 2024-03-30 | 2024-05-31 | 92 | 62 | Ask BC for updates, PNNL, Nathalie Voisin | Taylor dispatch to support new load data for 2023 and 2024. Ask Nathalie Voisin and PNNL. If we can define a process, we can ask hitachi to make GV enhancement | 120 | 2023-05-01 | 92 | 242 | 62
Load Shapes |  | 2018 shape and 2022 L&R monthly peak and energy | March-April | 2022-04-01 | Update load forecast | 2023-07-01 | 2024-01-31 | 2024-03-30 | 2024-05-31 | 214 | 62 |  |  | 181 | 2023-07-01 | 214 | 59 | 62
Demand Response Shapes |  | LBNL based off available DR from L&R and LMPs form 2032 ADS run |  | 2022-08-01 | Update at end of build | 2023-01-01 | 2023-03-01 | 2024-04-01 | 2024-05-31 | 59 | 60 |  | May need to have GV to dispatch | 0 | 2023-01-01 | 59 | 397 | 60
Energy Efficiency |  | Not used in 2032 |  | None | Update as needed, if available | 2023-01-01 | 2023-03-01 | 2024-04-01 | 2024-05-31 | 59 | 60 |  | Built into the load forecast, AAEE for CA, need CEC data | 0 | 2023-01-01 | 59 | 397 | 60
Pump loads |  | 2018 actuals obtained from CISO |  | 2022-02-01 | No change for this cycle | None | None | None | None | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Electric Vehicle loads |  | N/A |  | None | Updated if available | 2023-07-01 | 2024-01-31 | 2024-04-01 | 2024-05-31 | 214 | 60 |  | For CA layer in unique load shape as needed. Ask CA what they want to do for 2023 | 181 | 2023-07-01 | 214 | 61 | 60
Electrification Loads |  | N/A |  | None | Updated if available | 2023-07-01 | 2024-01-31 | 2024-04-01 | 2024-05-31 | 214 | 60 |  | For CA layer in unique load shape as needed | 181 | 2023-07-01 | 214 | 61 | 60
BTM PV |  |  |  |  | Updated if available | 2023-07-01 | 2024-01-31 | 2024-04-01 | 2024-05-31
BTM Storage |  |  |  |  | Updated if available | 2023-07-01 | 2024-01-31 | 2024-04-01 | 2024-05-31
Hourly Wind Shapes |  | NREL |  | 2022-05-01 | Update if needed, planned resources | 2023-07-01 | 2024-01-31 | 2024-04-01 | 2024-05-31 | 214 | 60 | Update with Wind Toolkit Data, test with units we have had issues with | review data quality with NREL to see if there is updated data | 181 | 2023-07-01 | 214 | 61 | 60
Hourly Utility Scale Solar shapes |  | NREL |  | 2022-05-01 | Add shapes for new planned resources | 2023-07-01 | 2024-01-31 | 2024-04-01 | 2024-05-31 | 214 | 60 |  |  | 181 | 2023-07-01 | 214 | 61 | 60
BTM PV Shapes and modeling methodology |  | NREL |  | 2022-05-01 | Needs to be evaluated. Update magitude, not the shapes | 2023-07-01 | 2024-01-31 | 2024-04-01 | 2024-05-31 | 214 | 60 |  | County by utility vs Area granularity | 181 | 2023-07-01 | 214 | 61 | 60
Thermal Plant Data | [5 empty] | TBD | TBD | TBD | TBD | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cycling Data (Start costs, other) |  | 2020 Intertek Report |  | 2020-05-01 | Check with Intertek on frequency of updates | TBD | TBD | TBD | TBD | #VALUE! | #VALUE! |  | Check with Intertek | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Min up/down time |  |  |  | 2020-05-01 | Check with Intertek on frequency of updates | TBD | TBD | TBD | TBD | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ramp Rates |  | 2020 Intertek Report |  | 2020-05-01 | Check with Intertek on frequency of updates | TBD | TBD | TBD | TBD | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Heat rates |  | CEC and Kevin Harris analysis of CEMS data |  | 2020-06-01 | Check with Intertek on frequency of updates | TBD | TBD | TBD | TBD | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Variable O&M for all thermal generator types |  |  |  |  | Check with Intertek | TBD | TBD | TBD | TBD
FOR |  | GADS pc-GAR |  | 2022-01-01 | Update, GADS PCgar | 2023-07-01 | 2024-01-31 | 2024-02-01 | 2024-05-31 | 214 | 120 |  |  | 181 | 2023-07-01 | 214 | 1 | 120
Natural Gas Prices |  | CEC 2021 IEPR | December | 2022-02-01 | Update | None | None | 2024-01-01 | 2024-03-01 | #VALUE! | 60 |  | Make change case available if data is available for V1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 60
Coal Prices |  | Inflated 2030 ADS prices |  | 2022-02-01 | Update | None | None | 2024-01-01 | 2024-03-01 | #VALUE! | 60 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 60
Uranium Prices |  | 2022 Price |  | 2022-02-01 | Update | None | None | 2024-01-01 | 2024-03-01 | #VALUE! | 60 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 60
Other fuels Prices |  | Inflated 2030 ADS prices |  | 2022-02-01 | Update | None | None | 2024-01-01 | 2024-03-01 | #VALUE! | 60 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 60
CO2 prices California |  | CEC 2021 IEPR | December | 2022-04-01 | Update | None | None | 2024-02-01 | 2024-05-31 | #VALUE! | 120 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 120
CO2 prices Washington Oregon |  |  |  | NA | Update, reach out to BPA | None | None | 2024-02-01 | 2024-05-31
CO2 prices BC and Alberta |  |  |  |  | Update | None | None | 2024-02-01 | 2024-05-31
Variable O&M for all Non-thermal generator types |  | INTERTEK Cycleing Cost Report |  | 2021-09-01 | Update | 2023-07-01 | 2024-01-31 | 2024-02-01 | 2024-05-31 | 214 | 120 |  |  | 181 | 2023-07-01 | 214 | 1 | 120
Dispatch price for wind, solar, and hydro (Also called oportunity cost) |  | INTERTEK Cycleing Cost Report |  | 2021-09-01 | Update | 2023-07-01 | 2024-01-31 | 2024-02-01 | 2024-05-31 | 214 | 120 |  |  | 181 | 2023-07-01 | 214 | 1 | 120
Deflator/Inflator rates |  | Moody's inflator |  | 2022-02-01 | Update | 2023-07-01 | 2024-01-31 | 2024-02-01 | 2024-05-31 | 214 | 120 |  |  | 181 | 2023-07-01 | 214 | 1 | 120
Load-Following and Regulation reserve calculations |  | PNNL |  | 2023-03-01 |  | None | None | 2024-05-30 | 2024-07-01 | #VALUE! | 32 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 32
Maintenance Schedule |  | WECC |  | 2022-07-01 | Update | 2023-07-01 | 2024-01-31 | 2024-02-01 | 2024-06-30 | 214 | 150 |  |  | 181 | 2023-07-01 | 214 | 1 | 150
Phase Shifter Transformers - How to treat, and review |  |  |  |  | Discuss Further | TBD | TBD | TBD | TBD | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Formulas:
V1 Number of days = DAYS([V1 - Implementation Schedule ADS-End],[V1 - Implementation Schedule ADS-Begin])
V2 Number of days = DAYS([V2 - Implementation Schedule ADS-End],[V2 - Implementation Schedule ADS-Begin])
V1-V2 Number of Days = DAYS([V2 - Implementation Schedule ADS-Begin],[V1 - Implementation Schedule ADS-End])