## RRC Three-Year Work Plan
Task Name | Description | Reliability Risk Priorities | Long-Term Strategy | Status | Start Date | Target Date | Complete Date | Task Lead | Task Support | Due Y | Comments | Status Update | Issues & Possible Solutions | Y | Q
RRC Outreach | Develop and implement an outreach plan to share the purpose, vision, and strategic objectives of the RRC. The goal of this outreach is to generate engagement, enrollment, and excitement about the RRC, thereby increasing participation in the RRC. Tim Reynolds and Vic Howell will outreach to groups internal and external to WECC. | 6: Committee Specific Priority | 3: Engage reliability & security community | Proceeding | 2023-01-01 | Revised to 10/1/2023 (from 5/1/2023) |  | RRC | WECC staff | 2023 |  | We have done 25 outreach presentations which includes WECC committees, WECC internal groups and all-hands meetings, and external groups (BPA staff, Western Chiefs meeting, RC West Oversight Committee, and WIRAB). There is one more presentation planned on November 1 at the WECC Reliability and Security Conference that will make a total of 26. | Only needed for items with the status of Assistance or Attention
RRC Risk Management Process | Develop RRC Risk Management Process to be used by the RRC to develop and maintain an ongoing, prioritized list of known and emerging reliability and security risks facing the Western Interconnection. | 6: Committee Specific Priority | 2: Assess & mitigate risks to reliability & security | Proceeding | 2022-03-01 | 2023-02-28 | 2023-02-28 | RRC Strike Team | RRC members | 2023 | RRC Risk Management Process presented at October 20, 2022, RRC meeting. | The RRC Risk Management Process was approved at the February 2023 meeting.
Initial List of Risks | Develop an initial list of known and emerging reliability and security risks facing the Western Interconnection using the newly developed RRC Risk Management Process. Determine and execute actions to address priority risks in accordance with the process. Tim Reynolds to lead and provide initial list for RRC review. | 6: Committee Specific Priority | 2: Assess & mitigate risks to reliability & security | Proceeding | 2023-01-01 | 2023-04-01 | 2023-06-28 | RRC | RRC subgroups | 2023 |  | Tim Reynolds presented the initial list of risks at June 2023 meeting for RRC review and input.
Committee Restructure | Support the implementation and transition to the new committee structure determined by the JGC. | 6: Committee Specific Priority | 3: Engage reliability & security community | Proceeding | 2023-01-01 | Undefined | 2023-08-04 | RRC | RRC subgroups | #INVALID DATA TYPE |  | The RRC approved revised charters and scopes at the 5/26/2023 meeting. The RRC approved further changes to the PS and OAWG charters at the June 2023 RRC meeting. The JGC endorsed all RRC and subgroup charters/scopes at the August JGC meeting.
Cybersecurity Best Practices | 1) Identify cybersecurity risks to critical infrastructure based on current research relevant to the electric utility industry (CISA, DOE, E-ISAC, InfraGard, etc.). Due date: Q2 2023 (completed). Ongoing updates: Q2 2024, Q2 2025. 2) Assess how these risks are being addressed by WECC member organizations using data gathered through WECC reliability assurance visits, CSWG member surveys, etc. Due date: Q3 2023. Ongoing updates: Q3 2024, Q3 2025. (Parallel with item 3). 3) Determine whether and how these risks are being addressed by other groups (e.g., NERC SWG) and identify opportunities for outreach to WECC member organizations. Due date: Q3, 2023. Ongoing updates: Q3 2024, Q3 2025. (Parallel with item 2). 4) Develop and conduct outreach events (conferences, webinars, white papers, etc.) to aid WECC member organizations in addressing these most critical, least addressed risks. Include structured follow-up to assess level of success. Due date (development): Q4 2023. Continuing (outreach): Q1 2024 – Q4 2025. 5) Provide resulting cybersecurity information (risks, trends, best practices, outreach efforts and results, etc.) to WECC member organizations, the RRC, and other interested WECC committees. Due date (development): Q1 2024. Continuing (outreach): Q2 2024 – Q4 2025. 6) CSGWG tasks due dates for work items listed above are due 90 days after the RRC work plan is finalized. (Completed). See "comments" column for questions to consider. | 1: Cybersecurity | 2: Assess & mitigate risks to reliability & security | Proceeding | 2023-01-01 | Dates by item | Item 1 completed 6/28/2023 | CSF |  | #INVALID DATA TYPE | Factors for CSWG to consider: 1) What reliability risks to the BPS are presented if there’s a cyber-hack at a specific entity? 2) What are the best practices for building new facilities to help protect against cyber-attacks? 3) Which cybersecurity risks present the greatest reliability risks to the BPS? 4) How are cybersecurity risks being addressed by groups outside of WECC (e.g., industry groups, regulatory groups, academia)? 5) Have conversations with the WECC Studies Subcommittee (StS) to consider whether there are planning studies that can or should be done to address cybersecurity threats. 6) Have conversations with NERC and the StS to consider how cybersecurity threats and reliability planning can come together. | Due dates for all work items have been developed, including follow-ups throughout the 3-year work plan (see item descriptions). Item 1 work product was presented to the RRC during the June 28-29, 2023, RRC meeting. Item 4 is partially addressed by the Power System Security Conference held at WECC offices on August 8-10. An in-person CSF and PSF meeting was held the last day of the conference.
Identify Strategic Initiatives for Extreme Natural Events | 1) Identify specific risk areas within the broader topic of “extreme natural events” that pose unique risks to the reliability of the Western Interconnection Bulk Power System (BPS) that, if addressed, would add the most value to stakeholders. Determine how best to collaborate with the RAC on this initiative. 2) Determine whether and how these specific risk areas are being addressed in the industry and determine how to share these learnings most effectively with stakeholders. 3) Based on this research, determine one or more specific risks the RRC should address via the RRC Risk Management Process. 4) Develop a Strike Team by February 2023, followed by developing a plan to identify specific tasks that can be completed within 12 months. See "comments" column for questions to consider. | 2: Extreme Natural Events | 2: Assess & mitigate risks to reliability & security | Proceeding | 2023-01-01 | Q2 2024 |  | RRC Strike Team |  | #INVALID DATA TYPE | Questions to consider: 1) What reliability impacts of extreme natural events exist for system operations? 2) What best practices already exist or are needed to address extreme natural events? 3) What types of system characteristics and conditions expose the interconnection to the greatest risk from natural events? | The strike team will continue to meet monthly through the end of 2023. The group is tentatively planning to finalize the list of Extreme Natural Events and associated Risks by the end of Q3 2023 with the focus on prioritizing the list of risks, evaluating the likelihood of the events to happen, the impact to the grid, and conducting outreach with specific NERC RISC members and RSTC Chair to determine if and how the risk areas are being addressed in other stakeholder groups and the industry. The goal is to have one or more specific risks identified early Q1 2024 to be addressed via the RRC Risk Management process.
Inverter-Based Resource Best Practices | Create one or more regional best practices documents from inverter-based resources (IBR) events. These documents would be most useful if they share solutions to challenges entities have overcome. A few possible topics to explore include: 1) Making changes to interconnection requirements, and enforcing those changes 2) Identifying and analyzing IBR event and work with GO on performance improvement 3) Efforts on model improvement (RAC is addressing this) 4) Checkoff list before energization 5) Providing guidance for Generator Owners and Operators as well as Transmission Operators and Balancing Authorities integrating IBRs as well as best practice documents for monitoring IBR performance once commercial operation begins. 6) EPAS to develop a plan by April 1. See "comments" column for questions to consider and context/background. | 4: Impacts of Changing Resources and Customer Loads on the BPS | 2: Assess & mitigate risks to reliability & security | Proceeding | 2023-01-01 | TBD |  | EPAS |  | #INVALID DATA TYPE | Questions to consider: 1) What reliability challenges have already been faced with IBRs, and what other challenges may emerge? 2) How have the resource changes already affected the reliability of the BPS? (Assignment to PWG?) 3) How do we make sure we aren’t duplicating work, make sure we are aware and aligned with NERC/FERC efforts, and make sure we are participating in guiding the development of future standards related to IBRs (including DERs)? Context and Background: IBRs have received much attention recently at both the NERC and regional levels. This is due to the aggressive increase in their contribution in the generation portfolio, especially in the Western Interconnection. These resources are attractive because they do not emit greenhouse gases, however, they also exhibit characteristics that contribute to the complexity of reliable operations of the grid. IBR performance during system disturbances, the non-dispatchable nature of these resources, and inaccurate modeling in the operations realm are just a few of the challenges industry is currently working on. The impact of IBRs has been identified as a regional risk priority. Some possible ways the Western Interconnection can address this concern is by being open amongst each other and learning from each other's experience. One effective way of doing this is by sharing experiences through the NERC Lessons Learned process. Sharing these experiences with peers can help them save time and money when addressing these issues. | At the June 2023 RRC meeting, Rich Bauer, NERC presented an overview of their work towards the challenges if integrating IBR facilities into the BES in a reliable manner. Given NERCs efforts, WECC EPAS will approach the RRC tasks in the following manner. Create one or more regional best practices documents from inverter-based resources (IBR) events. 1) Making changes to interconnection requirements, and enforcing those changes. Greg Park is taking the lead on this item. 2) Identifying and analyzing IBR event and work with GO on performance improvement. Alan Wahlstrom is taking the lead on items 2 and 5 due to their interrelated nature. 3) Efforts on model improvement (RAC is addressing this) 4) Checkoff list before energization Curtis Holland is taking the lead on this. Research into NERC efforts in this subject. 5) Providing guidance for Generator Owners and Operators as well as Transmission Operators and Balancing Authorities integrating IBRs as well as best practice documents for monitoring IBR performance once commercial operation begins. Alan Wahlstrom (see 2 above) EPAS will have open meetings as needed during the progress of this event.
Examine Variable Energy Resource (VER) Impacts to Operations Reliability | Understand and quantify any impacts that VERs have on operations reliability. These impacts will examine historical performance during normal and extreme temperature events and determine if there is a concern with the availability and deliverability of energy due to VER contributions. See "comments" column for questions to consider and context/background. | 4: Impacts of Changing Resources and Customer Loads on the BPS | 2: Assess & mitigate risks to reliability & security | Proceeding | 2023-01-01 | TBD |  | EPAS and PS (Tim Reynolds will take the lead initially) |  | #INVALID DATA TYPE | Questions to consider: 1) How do we measure the impacts that VERs are having on BA operations? 2) How might this work inform longer-term resource planning to ensure energy sufficiency? 3) Can any useful information be gleaned from examining trends and patterns in existing databases? (e.g., GADS/TADS, RC databases) 4) Can BAs benefit from having a wider-area view of interconnection resources during extreme temperature events? If BAs could benefit, what data is available and valuable? How would/should it be shared and used? What would be considered sensitive information with sharing restrictions? Context and background: The Western Interconnection has seen a large change in the resource mix in recent years. The increased penetration of variable resources accompanied by the retirement of traditional generators will continue. It is important for industry to identify risks associated with this transition and develop solutions to ensure reliability. Part of this consideration involves understanding the availability of these resources when the system is stressed. | Tim Reynolds reported at the June RRC meeting that WECC will be using Stanford Interns to assist in this analysis of data. The interns arrived in late June. Results of their analysis will help to inform further steps that need to be taken.
Investigate Long-Duration Frequency Deviations | Understand changes being observed in long-duration frequency deviations (e.g., a prolonged deviation that was not cause due to a generator trip) and its impacts to operations reliability. This is related to BAs CPS1/BAAL performance and Primary Inadvertent Interchange accumulations—(Data related to BAL-001, BAL-004-WECC). See "comments" column for questions to consider and context/background. | 4: Impacts of Changing Resources and Customer Loads on the BPS | 2: Assess & mitigate risks to reliability & security | Proceeding | 2023-01-01 | Initial data, trends, and analysis by October 2023 RRC meeting |  | PS |  | #INVALID DATA TYPE | Questions to consider: 1) What are the impacts of longer-term frequency deviations (as measured at an hourly level) to BAs? To the Western Interconnection? 2) What risks are posed by these longer-term frequency deviations? 3) What are the causes of these longer-term frequency deviations? 4) What are some potential solutions that could be implemented to address these deviations? 5) To what extent is interconnection frequency control an emerging risk that requires additional attention? 6) Are BAs experiencing an increase in ramping challenges? (NERC RS M6 analysis has identified an uptick in BAs experiencing ramping issues). If so, what solutions could be implemented to address these challenges? Is this an interconnection issue, a regional issue, or a BA-specific issue? Context and background: Another concern with the addition of VERs relates to frequency related measurements that may be showing undesirable performance trends starting to emerge. Understanding these potential challenges can help us respond in a timely manner. | As of June RRC meeting, no analysis has been completed yet but the team has gathered the frequency data for several years. The group will be formalizing the data required for this analysis and produce a schedule and metric to use.
Examine Current Energy Adequacy Assessment Practices | ITEM PAUSED - see Status Update for more info. Examine current energy adequacy assessment practices and investigate the need for new or improved assessments to ensure adequate energy in real-time operations. See "comments" column for questions to consider and context/background. | 3: Resource Adequacy | 2: Assess & mitigate risks to reliability & security | Proceeding | 2023-01-01 | TBD | N/A | RRC & RAC joint effort |  | #INVALID DATA TYPE | Questions to consider: 1) What kind of assessments are being done to ensure adequate energy in real-time operations? 2) What best practices or guidance can be developed and shared? Context and background: This speaks to the benefit of performing energy adequacy assessments which ensures sufficient resources are available to meet energy needs for all hours. | The RRC learned that there was a plan to assemble a committee to take on work in the resource adequacy space. Consequently, the RRC decided to hold off on tackling this 3-year work play item until that Resource Adequacy group was formed and give it to them. Months later, the decision was made to put together an Advisory Group under the RAC to help advise WECC on the resource adequacy assessments WECC does. It's not a stakeholder group that is looking broadly at resource adequacy issues. Therefore, it was determined that this group is not one that can take on the RRC 3-year work plan item. As a result, the RRC has no group that this work can be assigned to. Options considered: 1) RRC to move forward with assembling a strike team or a more formal Task Force 2) Drop it (or pause it) from our 3-year work plan Consensus RRCSC decision was to pause work on this, but keep our thumb on the pulse of standard development progress. This decision was driven by challenges stakeholders are facing with having resources available to dedicate.
NERC Inverter-based Resource Performance Subcommittee (IRPS) Information Sharing | Invite the NERC Inverter-based Resource Performance Subcommittee (IRPS) to present to RRC: objectives, accomplishments, current activities being performed, and initiatives the RRC can help support (SAR development/support, awareness of current efforts, etc.). | 4: Impacts of Changing Resources and Customer Loads on the BPS | 3: Engage reliability & security community | Proceeding | 2023-01-01 | 410349 | 2023-06-28 | RRC |  | 3023 | Context and Background: There are already well-established groups throughout the nation that are working on some of the issues surrounding IBRs. In lieu of establishing regional groups and potentially duplicating efforts, putting an unnecessary strain on already limited resources, a more efficient way to contribute to these efforts is to have interested individuals join these existing groups and provide ongoing feedback to the RRC. This would help provide exposure to the work these groups are addressing and enlist support from entities in the Western Interconnection. It is possible that committee assignments could result from these discussions. | Rich Bauer from NERC presented on this topic at the June 2023 meeting. He gave a presentation on existing work associated with IBR's and the efforts currently underway within the NERC IRPS.
2022-01-01
2023-01-01
2024-01-01
2025-01-01