## 2036_Tasks
|  |  | Input Field |  |  | Input Field
|  |  | 45901 | 45908
Data available | Data Source | Order | Month Start | Month Finish | Days from Start | Weeks to Implement | Status | Notes | V1/V2? | Task | Task | Task | Task | Task | Task
2025-09-01 |  | 1 | 2025-09-01 | 2025-09-08 | 7 | 1 |  |  | V1/V2 | Import Transmission from 2036 HS1 PF
Today |  | 2 | 2025-09-01 | 2025-09-15 | 14 | 2 |  |  | V1/V2 | Review pumping loads
Today | CEC | 3 | 2025-09-01 | 2025-09-29 | 28 | 4 |  |  | V1/V2 | Energy Efficiency - CEC | Electric Vehicles | Electrification Loads
Today | PNNL | 4 | 2025-09-01 | 2025-09-29 | 28 | 4 |  |  | V1 | Hydro Data - PNNL and Canada | Weekly energy, min, max, etc. | BC Hydro Data
2025-09-01 | L&R | 5 | 2025-09-01 | 2025-09-29 | 28 | 4 |  |  | V1 | Develop Load Shapes from (2025L&R)
2025-08-01 | L&R | 6 | 2025-08-01 | 2025-09-26 | 56 | 8 |  |  | V1 | Compare 2025L&R with 2024 L&R resources
2025-09-01 |  | 7 | 2025-09-01 | 2025-10-27 | 56 | 8 |  |  | V1 | Align L&R resources with power flow (2025L&R)
2025-09-01 |  | 8 | 2025-09-01 | 2025-10-27 | 56 | 8 |  |  | V1 | Place new units from L&R that were not in power flow (2025L&R) | Meet with APFTF on placed units and placement tool | APFTF approve placement
2025-09-01 | NREL/PNNL | 9 | 2025-10-01 | 2025-10-29 | 28 | 4 |  |  | V1 | BTM | BTM PV | BTM Storage | Methodology Area/County
2025-09-01 |  | 10 | 2025-10-01 | 2025-10-15 | 14 | 2 |  |  | V1 | Hourly shapes | Solar | Wind | Other
2025-09-01 | L&R/EIA | 11 | 2025-10-01 | 2025-10-15 | 14 | 2 |  |  | V1 | Pump Storage - Review charge time duration, rates, etc Review assumptions
2025-09-01 | Intertek, CEC, CEMS | 12 | 2025-10-01 | 2025-10-29 | 28 | 4 |  |  | V1 | Thermal Data | Cycling Data (Start costs, other) | Min up/down time | Ramp Rates | Heat rates | FOR
2025-09-01 | Intertek | 13 | 2025-11-01 | 2025-11-15 | 14 | 2 |  |  | V1 | VOM
2026-01-15 | WECC Path Rating Catalog | 14 | 2026-01-15 | 2026-02-12 | 28 | 4 |  |  | V1 | Path definitions/ratings - WECC Paths | WECC/Non WECC Paths
Today | Area request | 15 | 2025-11-01 | 2025-11-29 | 28 | 4 |  |  | V1 | Nomograms | EPE and TEPC load and generation balance nomograms
Today | OASIS OATI | 16 | 2025-11-01 | 2025-11-29 | 28 | 4 |  |  | V1/V2 | Wheeling Rates (from utility tariffs)
Today | CEC IEPR | 17 | 2025-11-01 | 2025-11-15 | 14 | 2 |  |  | V1 | Fuel Prices | Natural Gas Prices | Coal Prices | Uranium Prices | Other fuels Prices
Today | California DOF Deflator | 18 | 2025-11-01 | 2025-11-15 | 14 | 2 |  |  | V1 | Deflator/Inflator rates | California Department of Finance
Today | CEC IEPR | 19 | 2025-11-01 | 2025-11-15 | 14 | 2 |  |  | V1 | CO2 Prices | CO2 prices California | CO2 prices Washington Oregon | CO2 prices BC and Alberta
Today | Intertek | 20 | 2025-11-01 | 2025-11-15 | 14 | 2 |  |  | V1 | Dispatch price for wind, solar, and hydro (Also called oportunity cost)
|  | 21 | 2026-01-01 | 2026-01-29 | 28 | 4 |  |  | V1 | Draft runs of case
Today |  | 22 | 2026-01-01 | 2026-01-15 | 14 | 2 |  |  | V1 | Phase Shifter Transformers - How to treat, and review
Today |  | 23 | 2026-01-01 | 2026-01-15 | 14 | 2 |  |  | V1 | Load-Following and Regulation reserve calculations
Today |  | 24 | 2026-01-01 | 2026-01-15 | 14 | 2 |  |  | V1 | Maintenance Schedule
|  | 25 | 2026-02-01 | 2026-03-01 | 28 | 4 |  |  | V1 | ADS Case Review
|  | 26 | 2026-02-21 | 2026-02-28 | 7 | 1 |  |  | V1 | Post 2036 ADS PCM V1
2026-03-01 | PNNL | 27 | 2026-03-01 | 2026-03-29 | 28 | 4 |  |  | V2 | Hydro Data - PNNL and Canada | Weekly energy, min, max, etc. | BC Hydro Data
2026-03-01 | L&R | 28 | 2026-03-01 | 2026-03-29 | 28 | 4 |  |  | V2 | Develop Load Shapes from (2026L&R)
2026-03-01 | L&R | 29 | 2026-03-01 | 2026-04-26 | 56 | 8 |  |  | V2 | Bring in L&R Resources (2026L&R)
2026-03-01 |  | 30 | 2026-03-01 | 2026-04-26 | 56 | 8 |  |  | V2 | Align L&R resources with power flow (2026L&R)
2026-03-01 |  | 31 | 2026-03-01 | 2026-04-26 | 56 | 8 |  |  | V2 | Place new units from L&R that were not in power flow (2026L&R) | Meet with APFTF on placed units and placement tool | APFTF approve placement
2026-03-01 | NREL/PNNL | 32 | 2026-04-01 | 2026-04-29 | 28 | 4 |  |  | V2 | BTM | BTM PV | BTM Storage | Methodology Area/County
2026-03-01 |  | 33 | 2026-04-01 | 2026-04-15 | 14 | 2 |  |  | V2 | Hourly shapes | Solar | Wind | Other
2026-03-01 | L&R/EIA | 34 | 2026-04-01 | 2026-04-15 | 14 | 2 |  |  | V2 | Pump Storage - Review charge time duration, rates, etc
2026-03-01 | Intertek, CEC, CEMS | 35 | 2026-04-01 | 2026-04-29 | 28 | 4 |  |  | V2 | Thermal Data | Cycling Data (Start costs, other) | Min up/down time | Ramp Rates | Heat rates | FOR
2026-03-01 | Intertek | 36 | 2026-05-01 | 2026-05-15 | 14 | 2 |  |  | V2 | VOM
2026-03-01 | WECC Path Rating Catalog | 37 | 2026-05-01 | 2026-05-29 | 28 | 4 |  |  | V2 | Path definitions/ratings - WECC Paths | WECC/Non WECC Paths
2026-03-01 | Area request | 38 | 2026-05-01 | 2026-05-29 | 28 | 4 |  |  | V2 | Nomograms | EPE and TEPC load and generation balance nomograms
2026-03-01 | CEC IEPR | 39 | 2026-05-01 | 2026-05-15 | 14 | 2 |  |  | V2 | Fuel Prices | Natural Gas Prices | Coal Prices | Uranium Prices | Other fuels Prices
2026-03-01 | California DOF Deflator | 40 | 2026-05-01 | 2026-05-15 | 14 | 2 |  |  | V2 | Deflator/Inflator rates | California Department of Finance
2026-03-01 | CEC IEPR | 41 | 2026-05-01 | 2026-05-15 | 14 | 2 |  |  | V2 | CO2 Prices | CO2 prices California | CO2 prices Washington Oregon | CO2 prices BC and Alberta
2026-03-01 | Intertek | 42 | 2026-05-01 | 2026-05-15 | 14 | 2 |  |  | V2 | Dispatch price for wind, solar, and hydro (Also called oportunity cost)
|  | 43 | 2026-06-01 | 2026-06-29 | 28 | 4 |  |  | V2 | Draft runs of case
2026-03-01 | NERC GADS PC-gar | 44 | 2026-06-01 | 2026-06-15 | 14 | 2 |  |  | V2 | EFORd
2026-03-01 |  | 45 | 2026-06-01 | 2026-06-15 | 14 | 2 |  |  | V2 | Load-Following and Regulation reserve calculations
2026-03-01 | LBNL | 46 | 2026-06-01 | 2026-06-29 | 28 | 4 |  |  | V2 | Demand Response Shapes - Must have a full run
2026-03-01 |  | 47 | 2026-06-01 | 2026-06-15 | 14 | 2 |  |  | V2 | Phase Shifter Transformers - How to treat, and review
2026-03-01 |  | 48 | 2026-06-01 | 2026-06-15 | 14 | 2 |  |  | V2 | Maintenance Schedule
|  | 49 | 2026-06-01 | 2026-06-29 | 28 | 4 |  |  | V2 | ADS Case Review
|  | 50 | 2026-06-01 | 2026-06-22 | 21 | 3 |  |  | V2 | Create ADS PF
|  | 51 | 2026-06-23 | 2026-06-30 | 7 | 1 |  |  | V2 | Post 2036 ADS PCM V2
Formulas:
Month Finish = [Month Start]+([Weeks to Implement]*7)
Days from Start = IFERROR(DAYS([Month Finish],[Month Start]),)

## 2036_PCDS_DecisionDiscussion
Item | Detail | PCDS Decision | List of things we need to accomplish |  | Build year10, then year 20 | People | ADS doenloads | Survey
Resource Modeling in PCM | How to model resources: Keep all PF units, Keep only L&R units? Which data from each(PF,L&R,EIA), Pmax, location, comission/Retirement | Keep all pf units in PCM | If not on list, exception process, RAC approval |  | Year 20, in 2027 | People | confindeital request form
Resource Modeling in PCM | PCDS decision/approval on placing units in L&R, but not in PF. Approval of placment tool logic |  | Internal sit down - what else do we need to accomplish, enhancements, documantation | documentation, |  | For focus group
Review list of ADS Tasks
| Adding transmission projects | Case by case basis |  |  |  | Whos using this V3.1 ADS, is it too late.
| Create V1 case | Yes
| Weather year | 2018 Bring up in future meetings
| Keeping in all PF units in PCM case | Yes
| ADS every year instead of V1, adjust PF schedule for earlier release of pf, Rename V1(Initital version)? |  |  |  |  | Schedule survery
| LID - EIA Plant Code - EIA Unit Code -EIA Generator ID - Name….....EIA Generator ID or L&R unit ID |  |  |  |  | Enochs list of confidential request form
ADS downloads