## Post-Release Issues
Issue/Observation | Comments | Lead Responsibility | Expected completion date | PCDS Follow-up date | Status | Column1
Reserve requirements have not been revised from 2030 ADS | Create reserve requirements, to be updated by PNNL | PNNL | 2022-12-15 |  | Ongoing
Batteries are modeled as pump storage in GridView. Consider using the new battery model in GridView Hyrbrid Battery modeling | Discussion with PCDS and recommendatoin about using new model | PCDS, | TBD | 2022-10-26 | Ask Hitachi to present if this will contribute to enhanced representation | close out informative tasks for this cycle, recommend to consider for next cycle.
Capacities - If we reference a Heavy Summer PF case for the PCM, the ratings will be derated for summer vs referencing a Winter PF case. | Will take some time to build, need to see if a case can be built. Need to be addressed in APFWG | PCDS, APFWG, Tyler | TBD | 2022-11-02 | Tyler to follow-up with Nick For information purposed for Round-Trip | close out informative tasks for this cycle, recommend to consider for next cycle.
Non dispatchable supply. The PCDS has not approved assumptions regarding the modeling of geothermal supply. Currently it is modeled as dispatchable with a zero cost dispatch cost. A scenario is provided to convert geothermal supply to fix energy supply where monthly generation is based on historic five year average generation by month. | Approve assumptions on modeling geothermal supply | PCDS, Kevin | TBD | 2022-10-26 | PCDS discussion needs to take place. Kevin would need to present. Complete, change case created, will be in V2.2
Possible Path 42 rating increase | Create change file with rating of 1,400 MW | WECC, Jon | 2022-09-28 |  | WECC will provide change case, complete
DCI - Virgina - Smith (0MW into WECC every hour). Should this be modified? Check other DC Ties | If no information, may need to use other DCI profile | PCDS, Jamie | TBD | TBD | PCDS discussion, follow-up with Heidi Pacini -Complete
PF, PCM, and L&R differ. Need to know what to do when PCM capacity is lower than L&R. | What do we do when the PCM is lower than the L&R? | PCDS, Tyler, Jamie | TBD | 2022-11-02 | Show that on PF export, are there any violations. Tyler will create report. Jamie will investigate. | close out informative tasks for this cycle, recommend to consider for next cycle.
Facilities with multiple owners have different assumptions about retirement dates | Resolve discrepancies regarding retirement dates between owners | PCDS | TBD | 2022-11-02 | PCDS discussion | close out informative tasks for this cycle, recommend to consider for next cycle.
BPA have raised concerns about the case using a CO2 price of $0 for OR and WA | Clarify that the current price is $0 but can be changed via change cases | PCDS, Jamie, Kevin | TBD | 2022-11-02 | Presented in PCDS, Ongoing Kevin and Jamie to present on findings | close out informative tasks for this cycle, recommend to consider for next cycle.
Pumped Storage Generic in CISO. How much pondage, etc. What should parameters be? |  | PCDS, Tyler, Yi | TBD | 2022-11-02 | PCDS discussion, follow-up with Yi -Keep as is. Complete
There is uncertainty about whether the Craig unit, currently not in the case, should be retired. | Determine whether Craig should be retired. Keep Retirement, may be converted to gas. Keep as in for now. | PCDS | TBD |  | Need decision from PCDS - In email from WACM, they suggested to not include since it will most likely be retired | close out informative tasks for this cycle, recommend to consider for next cycle.
Allow spillage on hydro plants 100 MW+ outside CA | Change file provided to allow spill on units 100 MW+ plants except on core columbia units Is unique to location, would need data collection. | PCDS | 2022-11-02 |  | Complete, Will provide an optional change case
Clean up data not used. | **Unused Pump storage plants **Generators in hourly general or other general tables that no longer exist in the database | WECC, Tyler, Jon | 2022-10-14 |  | Some of this is done, more to be done | close out informative tasks for this cycle, recommend to consider for next cycle.
Update spillage for BANC Hydro according to data received | Make changes for next release | WECC, Tyler | 2022-10-14 |  | Complete, Will be in next release
Phase Shifters in Southern Utah being modeled as transformers | Get information to model as phase shifters | Tyler | 2022-10-12 | 2022-10-12 | Testing being done. Complete
23 batteries only have one hour storage | Change to 4-hour storage | WECC, Arkadeep Das | 2022-09-30 |  | Complete, Will be in next release
Thermal generator starts | Determine if the number of starts is appropriate | PCDS |  | 2022-10-12 | Complete
Some Geothermal generators aren't must run | Make all Geothermal must run | WECC, Arkadeep Das | 2022-10-14 |  | Complete, Will be in next release
San Diego generator, Big Rock Solar, needs to move from 23284 to 22356 | Move generator when creating a new PF and move in PCM | WECC: Tyler, Nick |  |  | complete
Change EPE balance nomogram to penalty of $20 | Suggestion from Jin since a high penalty. This affects the LMP, weighted by generator. | WECC: Tyler |  |  | Complete, change case created
B2H Boardman to Hemmingway |  |  |  |  | complete
Include Clearwater wind 750 MW | PCDS decided to add this on 11/30/2022 meeting |  |  |  | Complete

## Completed
Issue/Observation | Comments | Lead Responsibility | Expected completion date | Status
Explain or resolve capacity differences between the PCM, L&R and PF | Used VAR Margin Ration to Lower PCM to match PF |  | NA | Complete
There are discrepancies between PF and L&R for Columbia River Gorge units including Grand Coulee. Need to resolve discrepancies between PF and L&R capacities | PCDS decided to make changes according to Anders information | WECC | 2022-09-15 | Complete, Implemented data from Anders
Round trip export capability out of GV doesn't read into PSLF | Correct GridView to enable ability to read exported hour into PSLF | Hitachi | TBD | Complete
Update Demand Response Shapes to integrate into case |  | LBNL, staff | NA | Complete
The high CO2 cost provided by AESO results in Alberta importing heavy from the US market. Given the uncertainty in this developing CO2 market PCDS | Change to BC CO2 price |  | NA | Complete
There exist uncertainty as to the future of Colstrip 3 and 4. Some of the current owners have reported terminating/retiring their share of Colstrip facility. Currently x MW are reported in the L&R there the PCDS recommended that only one unit be operational in the base case (Unit 4). WECC has provided two scenarios, one to turn on Colstrip 3 and the second to turn off Colstrip 4 | Adopt consistent assumptions regarding Colstrip retirements | PCDS | 2022-09-28 | Complete, Change files provided as part of the 2032 ADS PCM V2.1 Case
LADWP DMS disagreement | LADWP said to leave as is |  | NA | Complete
NEVP Basecase Modification | Integrated into case |  | NA | Complete
Derate2 and Derate3 have whole numbers instead of percentage | Correct the derate to a percentage |  | NA | Complete
Tracy pump modeled as load in PF and generators in PCM | Resolve between Hitachi and PCDS | WECC | NA | Complete - Change case created to turn off loads in PCM. Also added the generators to the PF
Changes to bus and or Gen ID for some units to algin with PF |  | WECC | NA | Complete - Change case created
PSCO Generator Updates |  | WECC | NA | Complete
CFE generator Updates |  | WECC | NA | Complete
DCI Stegall, Artesia, and Miles City are modeled as load in PF and generators in the PCM | The reference PF now has these units added as generators | PCDS | TBD | Complete
Do not allow spill outside of California | Complete in ADS PCM V2.1 | WECC |  | Complete

## Next Cycle Opportunities
Issue/Observation | Comments | Lead Responsibility | Expected completion date | PCDS Follow-up date | Status | Column1
Batteries are modeled as pump storage in GridView. Consider using the new battery model in GridView Hyrbrid Battery modeling | Discussion with PCDS and recommendatoin about using new model | PCDS, | TBD | 2022-10-26 | Ask Hitachi to present if this will contribute to enhanced representation | close out informative tasks for this cycle, recommend to consider for next cycle.
Capacities - If we reference a Heavy Summer PF case for the PCM, the ratings will be derated for summer vs referencing a Winter PF case. | Will take some time to build, need to see if a case can be built. Need to be addressed in APFWG | PCDS, APFWG, Tyler | TBD | 2022-11-02 | Tyler to follow-up with Nick For information purposed for Round-Trip | close out informative tasks for this cycle, recommend to consider for next cycle.
PF, PCM, and L&R differ. Need to know what to do when PCM capacity is lower than L&R. | What do we do when the PCM is lower than the L&R? | PCDS, Tyler, Jamie | TBD | 2022-11-02 | Show that on PF export, are there any violations. Tyler will create report. Jamie will investigate. | close out informative tasks for this cycle, recommend to consider for next cycle.
Facilities with multiple owners have different assumptions about retirement dates | Resolve discrepancies regarding retirement dates between owners | PCDS | TBD | 2022-11-02 | PCDS discussion | close out informative tasks for this cycle, recommend to consider for next cycle.
BPA have raised concerns about the case using a CO2 price of $0 for OR and WA | Clarify that the current price is $0 but can be changed via change cases | PCDS, Jamie, Kevin | TBD | 2022-11-02 | Presented in PCDS, Ongoing Kevin and Jamie to present on findings | close out informative tasks for this cycle, recommend to consider for next cycle.
There is uncertainty about whether the Craig unit, currently not in the case, should be retired. | Determine whether Craig should be retired. Keep Retirement, may be converted to gas. Keep as in for now. | PCDS | TBD |  | Need decision from PCDS - In email from WACM, they suggested to not include since it will most likely be retired | close out informative tasks for this cycle, recommend to consider for next cycle.
Clean up data not used. | **Unused Pump storage plants **Generators in hourly general or other general tables that no longer exist in the database | WECC, Tyler, Jon | 2022-10-14 |  | Some of this is done, more to be done | close out informative tasks for this cycle, recommend to consider for next cycle.